## PF NCSR Status Log (hidden)
Versum/EMD Quote # | Customer Location | Customer PO# | Customer PO Received Date | Supplier | Probablity | Supplier PO# or Production Order | Revenue | Finish Date | MM# | Equipment # | Serial # | Description | Tool ID# | Status | Tracking Number from CM | IP Addresses Received? | Confidence Level | NCSR Date | ECR# | Submitted By: | Functional or Cosmetic | Short Description | Nonconformance Description | Reason for Aceptance | Approved NCSR Link | Customer Approval (Tool Owner) | Approval Commercial Rep. (Init/Date) | Approval PF Exec Mgr. (Init/Date) | Approval Operations (Init/Date) | Approval Quality (Init/Date) | Drawing Number | Discrepant Part Mfg. | Discrepant Part Number | Part Location/I.D. | Part Quantity | Contract Manufacturer | Discrepant Part Status | Tracking # from Supplier to Vultee | Tracking # from Vultee to FSE | Notification to Robin (Where shipped) | Work Instruction Required? | Work Instruction Identifier | FSE Field Service Completion Date | Comments
Q-18804R1 | Intel/Oregon/D1X | 5906008483 | 2021-05-04 | TPC | 70% | 4500101154 |  | 2021-08-02 | 2310629 | 200445930 | 1 | EQ_ACDSys_LGDSB++_+MF++PPG++D+++++_2++A | UM051 | Ready for packing/crating |  | N/A |  |  | 67500 | BR Klees | Functional | Manual Valve | Shipped with Non-Conformance: 3/8” Manual Valve | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. | Yes | [6 empty] | Entegris | 201-46-01-3 |  | 2 | TPC | 2021-10-27 |  |  |  | Yes | Installation Procedure for Entegris HV064 HV065_20210729
Q-19026 | Intel/Arizona | 5906010831 | 2021-05-13 | TPC | 70% | 4500099832 |  | 2021-08-20 | 486138 | 200445632 | 2 | EQ_ACDSys_LGD+B++_+NLG+++GC+++++FS_2++B | GX121 | PULL IN: Date shift from 9/24 to 8/20, NCR created for flow controllers |  | Y |  |  | 67500 | BR Klees | Functional | Manual Valve | Shipped with Non-Conformance: 3/8” Manual Valve | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. | Yes | [6 empty] | Entegris | 201-46-01-3 |  | 2 | TPC | 2021-10-27 |  |  |  | Yes | Installation Procedure for Entegris HV064 HV065_20210729
Q-19026 | Intel/Arizona | 5906010831 | 2021-05-13 | TPC | 70% | 4500099832 |  | 2021-08-20 | 486138 | 200445632 | 2 | EQ_ACDSys_LGD+B++_+NLG+++GC+++++FS_2++B | GX121 | PULL IN: Date shift from 9/24 to 8/20, NCR created for flow controllers |  | Y |  |  | 67697 | BR Klees | Functional | Flow Controller | Flow controller with same flow range but different port size – Need to investigate stock. Another potential is to just install 1 flow controller instead of 2. |  | Yes | [6 empty] | Entegris | 6500-T6-F04-D12-K-P7-U3 (1.1) |  | 2 | TPC | 4ea 12/22 SemiTorr shipout 4ea No Confirmation
Q-18803 | Intel/Oregon/D1X | 5906008483 | 2021-04-14 | TPC |  | 4500096943 |  | 2021-09-02 | 2309586 | 200445109 | 2 | EQ_ACDSys_LGDSB++_AML++++G++++++F+_2++A | XF051 | Tool ID name changed from HG051 to XF051 |  | Y |  |  | 67500 | BR Klees | Functional | Manual Valve | Shipped with Non-Conformance: 3/8” Manual Valve | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. | Yes | [6 empty] | Entegris | 201-46-01-3 |  | 2 | TPC | 2021-10-27 |  |  |  | Yes | Installation Procedure for Entegris HV064 HV065_20210729
Q-18803 | Intel/Oregon/D1X | 5906008483 | 2021-04-14 | TPC |  | 4500096943 |  | 2021-09-24 | 2305742 | 200445108 | 3 | EQ_ACDSys_LGDSB++_ANJ++++G++++++F+_2++A | RB051 | PUSH OUT: Date shift from 9/2 to 9/24 | [5 empty] | BR Klees | Functional | Power Supply | MOC 22510: Part change: P/N 90451063, AC/DC power supply converter. Supplied by PARTICLE MEASURING SYSTEM, The part model BB-SMi6-12-V-P230-C1 manufactured by BB SmartWorx , now it is changed to BB-SMi6B12V-P230C1. The two power supplies are visually different but functional identical. Spec sheets are attached. SAP# will remain the same as PMS is not changing its p/n. This change applies to Flowmaster LG | Older part no longer available |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | PMS | 90451063 |  | 2 | TPC | New part is installed in tool. Waiting for approval of PCN 261. | N/A, new style at TPC | N/A ships with tool |  | N/A |  |  | PCN 261 approved, no NCSR required
Q-18803 | Intel/Oregon/D1X | 5906008483 | 2021-04-14 | TPC |  | 4500096943 |  | 2021-09-24 | 2305742 | 200445108 | 3 | EQ_ACDSys_LGDSB++_ANJ++++G++++++F+_2++A | RB051 | PUSH OUT: Date shift from 9/2 to 9/24 |  |  |  |  | 67500 | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Entegris | 201-46-01-3 |  | 2 | TPC | 2021-10-27 |  |  |  | Yes | Installation Procedure for Entegris HV064 HV065_20210729
Q-19027 | Intel/Arizona | 5906010831 LI 14 | 2021-05-19 | TPC |  | 4500101310 |  | 2021-09-24 | 488050 | 200445971 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++FS_2++A | VC121D | PULL IN: Date shift from 10/5 to 9/24 |  | N/A |  |  |  | BR Klees | Functional | Power Supply | MOC 22510: Part change: P/N 90451063, AC/DC power supply converter. Supplied by PARTICLE MEASURING SYSTEM, The part model BB-SMi6-12-V-P230-C1 manufactured by BB SmartWorx , now it is changed to BB-SMi6B12V-P230C1. The two power supplies are visually different but functional identical. Spec sheets are attached. SAP# will remain the same as PMS is not changing its p/n. This change applies to Flowmaster LG | Older part no longer available |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | PMS | 90451063 |  | 2 | TPC | New part is installed in tool. Waiting for approval of PCN 261. | N/A, new style at TPC | N/A ships with tool |  | N/A |  |  | PCN 261 approved, no NCSR required
Q-19027 | Intel/Arizona | 5906010831 LI 14 | 2021-05-19 | TPC |  | 4500101310 |  | 2021-09-24 | 488050 | 200445971 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++FS_2++A | VC121D | PULL IN: Date shift from 10/5 to 9/24 |  | N/A |  |  | 67500 | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Entegris | 201-46-01-3 |  | 2 | TPC | 2021-10-27 |  |  |  | Yes | Installation Procedure for Entegris HV064 HV065_20210729
Q-19027 | Intel/Arizona | 5906010831 LI 14 | 2021-05-19 | TPC |  | 4500101310 |  | 2021-09-24 | 488050 | 200445971 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++FS_2++A | VC121D | PULL IN: Date shift from 10/5 to 9/24 |  | N/A |  |  |  | BR Klees | Functional | Flow Controller | Flow controller unavailable by ship date. Test tool with Golden Tool FC, install FC in field. | Maintain shipment schedule |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Entegris | 6500-T1-F02-D12-K-P7-U3 (1.1) |  | 1 | TPC | 2022-01-06
| Intel/Arizona | 5906010831 LI 14 | 2021-05-19 | TPC |  | 4500101310 |  | 2021-09-24 | 488050 | 200445971 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++FS_2++A | VC121D | PULL IN: Date shift from 10/5 to 9/24 | [5 empty] | BR Klees | Functional | HMI | Allen Bradley HMI deliver date shift to 9/30 | F series HMI expect to arrive TPC on end of September |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Allen Bradley | 6181P-15A3SW71AC |  | 2 | TPC | 2021-10-12
Q-18189R3 | Intel/Oregon/D1X | 5906008483 | 2021-03-11 | TPC |  | 4500095621 |  | 2021-09-22 | 2305742 | 200444937 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++F+_2++A | CX051 | Enclosure is being built. |  | Y |  |  | 67500 | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Entegris | 201-46-01-3 |  | 2 | TPC | 2021-10-27 |  |  |  | Yes | Installation Procedure for Entegris HV064 HV065_20210729
Q-19028 | Intel/Arizona | 5906010831 LI 11 | 2021-05-19 | TPC |  | 4500101152 |  | 2021-10-29 | 486134 | 200445929 | 3 | EQ_ACDSys_LGD+B++_+NJ++++G++++++F+_2++A | FB122D | Updating MBOM for new filter vent option | [5 empty] | BR Klees | Functional | Flow Controller | Short flow controllers | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | 6501-T8-F06-D12-K-P7-U3-M36 |  | 2 | TPC | 2021-12-17 | [6 empty] | 10/1 - FC location at FC021、FC025.(10/5)
Q-19028 | Intel/Arizona | 5906010831 LI 11 | 2021-05-19 | TPC |  | 4500101152 |  | 2021-10-29 | 486134 | 200445929 | 3 | EQ_ACDSys_LGD+B++_+NJ++++G++++++F+_2++A | FB122D | Updating MBOM for new filter vent option | [5 empty] | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | 201-46-01-3 |  | 2 | TPC | 2021-10-27 |  |  |  | Yes | Installation Procedure for Entegris HV064 HV065_20210729 |  | 10/1 - Does not match Jason's ist of deficient parts. Need to confirm. 10/5 --> Manual valve cantnot meet assembly schedule, therefore, shipped with NCSR; and will be sent to EMD after TPC arrives. Location at HV064、HV065.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Flow Controller | Short flow controllers | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | 6501-T8-F06-D12-K-P7-U3-M36 |  | 2 | TPC | 2021-12-17 | [6 empty] | 10/1 - Which FC? 10/5 FC location at FC121、FC221.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Filter Housing | Short filter housings | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Pall | FPT10-3/4FL-1/4FL |  | 2 6 | TPC | 2021-12-30 | [6 empty] | 10/5 Location at FL101、FL102、FL201、FL202、FL021、FL022.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Flow Controller | Short flow controllers | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | 6500-T4-F03-D12-K-P7-U3 (1.1) |  | 2 | TPC | 2021-12-30 | [6 empty] | 10/1 - Which FC location/ID? 10/5 FC location at FC122、FC222.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Check Valve | Short check valves | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | CK8-8F-8F |  | 6 2 | TPC | 2022-05-20 | [6 empty] | 10/5 Location at KV003、KV004.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Particle Counter | Short particle counters | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | PMS | 301070-0312 |  | 1 | TPC | 2021-11-02 | [6 empty] | 10/1 - Allwiring/mechanical work completed? 10/5 The LPC cover has been installed. Location at LPC01.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | 201-97-01-3 |  | 2 | TPC | 2021-11-19 |  |  |  |  | Installation Procedure for Entegris HV064 HV065_20210729 |  | 10/1 - Does this require a different procedure from the one shown in cell AQ? 10/5 The installation steps of HV025 and HV026 are different from the AQ field, and TPC will provide new installation instructions. Location at HV025、HV026.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Pressure Vessel | Short pressure vessel | Will use pressure vessels from KF112 for testing and shipment. Swap pressure vessels into KF112 in field. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | 153-601-156 |  | 4 | TPC | 2022-02-23 |  |  |  | Yes |  |  | 10/1 - Need some instruction from TPC to guide Robin's team on pressure vessel location and installation. 10/5 VSL installation instructions will be provided before the machine is released. Location at VSL101, VSL102 VSL201, VSL202.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Entegris | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 8 |  | 2021-10-15 | [6 empty] | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Entegris | DS12-2M-12F-3 | HV104. | 1 |  | 2021-12-29 | [6 empty] | 10/5- Location at HV104.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | 3 way valve | Short 3-way valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Entegris | D8-3C-12F-3 | CV026、CV036、CV042 | 3 |  | 2021-10-26 | [6 empty] | 10/5- Location at CV026、CV036、CV042.
Q-19025 | Intel/Oregon/D1X | 5906010831 LI 12 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-27 | 2305744 | 200445968 | 5 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | NX051 | PULL IN: Date shift from 12/1 to 10/27 |  | N/A |  |  |  | BR Klees | Functional | Flow Controller |  |  |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | 6501-T8-F06-D12-K-P7-U3-M36 |  | 2 | TPC | 2021-12-17
Q-19025 | Intel/Oregon/D1X | 5906010831 LI 12 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-27 | 2305744 | 200445968 | 5 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | NX051 | PULL IN: Date shift from 12/1 to 10/27 |  | N/A |  |  |  | BR Klees | Functional | Flow Controller |  |  |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Entegris | 6500-T4-F03-D12-K-P7-U3 (1.1) | FC122、FC222 | 2 | TPC | 2021-12-30 | [6 empty] | 10/1 - Location of FC's 10/5- FC location at FC122、FC222.
Q-19025 | Intel/Oregon/D1X | 5906010831 LI 12 | 2021-05-19 | TPC |  | 4500101309 |  | 2021-10-27 | 2305744 | 200445968 | 5 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | NX051 | PULL IN: Date shift from 12/1 to 10/27 |  | N/A |  |  |  | BR Klees | Functional | Filter Housing |  |  |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Pall | FPT10-3/4FL-1/4FL | FL101、FL102、FL201、FL202、FL021、FL022 | 2 6 | TPC | 2021-12-30 | [6 empty] | 10/5- Location at FL101、FL102、FL201、FL202、FL021、FL022.
Note on AM2: Bernard Klees:9/30 Changed from October 6 delivery to TPC
Note on AM10: Bernard Klees:9/30 Changed from ETA TPC: Dec. 28th
Note on AM11: Bernard Klees:9/30 Updated from end of september to 10/12/21
Note on AM16: Bernard Klees:9/30 Changed from 4ea 9/15 8ea 12/15
Note on AM17: Bernard Klees:9/30 Changed from 4ea 9/15 8ea 12/15
Note on N25: Bernard Klees: Changed from KF122 10/8/21
Note on N26: Bernard Klees: Changed from KF122 10/8/21
Note on N27: Bernard Klees: Changed from KF122 10/8/21
Note on AM27: Bernard Klees:9/30 Changed from 4ea 9/15 8ea 12/15

## Sheet1
Sum of Part Quantity
Component | Discrepant Part Mfg. | Discrepant Part Number | Total
12 STA MANIFOLD ASSY | SMC | SS5Y31-03-DUX00330 | 2
|  | SS5Y31-12-DUX00013 | 14
3 STA MANIFOLD ASSY | SMC | SS5Y31-03-DUX00330 | 1
|  | SS5Y31-06-DUX00035 | 2
Flow Controller | ENTEGRIS | 6500-T1-F02-D12-K-P7-U3 (1.1) | 1
|  | 6500-T2-F03-D12-K-P7-U3 (1.1) | 3
|  | 6500-T3-F03-D12-K-P7-U3 (1.1) | 2
|  | 6500-T4-F03-D12-K-P7-U3 (1.1) | 4
|  | 6500-T6-F04-D12-K-P7-U3 (1.1) | 2
|  | 6500-T6-F04-D12-K-P7-U3 (1.1) | 2
|  | 6501-T8-F06-D12-K-P7-U3-M36 | 9
| ENTEGRIS | 6500-T0-F02-D12-K-P7-U3 | 2
|  | 6500-T1-F03-D12-K-P7-U3 (1.1) | 4
|  | 6500-T2-F03-D12-K-P7-U3 (1.1) | 4
|  | 6500-T3-F04-D12-K-P7-U3 (1.1) | 5
|  | 6501-T8-F06-D12-K-P7-U3-M36 | 8
Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | 2
|  | 6500-T0-F02-D12-K-P7-U3 | 1
|  | 6500-T1-F03-D12-K-P7-U3 (1.1) | 4
|  | 6500-T2-F03-D12-K-P7-U3 (1.1) | 4
|  | 6500-T3-F03-D12-K-P7-U3 (1.1) | 2
|  | 6500-T4-F04-D12-K-P7-U3 | 4
|  | 6500-T4-F04-D12-K-P7-U3 (1.1) | 3
|  | 6500-T5-F04-D12-K-P7-U3 (1.1) | 2
|  | 6500-T6-F04-D12-K-P7-U3 (1.1) | 2
|  | 6501-T8-F06-D12-K-P7-U3-M36 | 18
| ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | 2
|  | 6500-T5-F04-D12-K-P7-U3 (1.1) | 8
Grand Total |  |  | 117

## PF_NCSR Status Log
Versum/EMD Quote # | Customer Location | Customer PO# | Customer PO Received Date | Supplier | Supplier PO# or Production Order | Finish Date | MM# | Equipment # | Serial # | Description | Tool ID# | Status | Tracking Number from CM | IP Addresses Received? | Confidence Level | NCSR Date | ECR# | Submitted By: | Functional or Cosmetic | Short Description | Nonconformance Description | Reason for Aceptance | Approved NCSR Link | Customer Approval (Tool Owner) | Approval Commercial Rep. (Init/Date) | Approval PF Exec Mgr. (Init/Date) | Approval Operations (Init/Date) | Approval Quality (Init/Date) | Drawing Number | Component | Discrepant Part Mfg. | Discrepant Part Number | Part Location/I.D. | Part Quantity | Part Est Ship Date | ECR# | Contract Manufacturer | Tracking # from Supplier to Vultee | Tracking # from Vultee to FSE | Tracking # from Supplier to FSE | Notification to Robin (Where shipped) | Work Instruction Required? | Work Instruction Identifier | FSE Field Service Completion Date | Tool Owner | Open Closed | Comments
Q-18804R1 | Intel/Oregon/D1X | 5906008483 | 2021-05-04 | TPC | 4500101154 | 2021-08-02 | 2310629 | 200445930 | 1 | EQ_ACDSys_LGDSB++_+MF++PPG++D+++++_2++A | UM051 | Ready for packing/crating |  | N/A |  |  | 67500 | BR Klees | Functional | Manual Valve | Shipped with Non-Conformance: 3/8” Manual Valve | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. | Yes | [6 empty] | Manual Valve | ENTEGRIS | 201-46-01-3 | HV064, HV065 | 2 | 2021-11-10 |  | TPC | 775049497664 | 523339839211 |  | 2021-11-04 | Yes | Installation Procedure for Entegris HV064 HV065_20210729 |  |  | Closed
Q-19026 | Intel/Arizona | 5906010831 | 2021-05-13 | TPC | 4500099832 | 2021-08-20 | 486138 | 200445632 | 2 | EQ_ACDSys_LGD+B++_+NLG+++GC+++++FS_2++B | GX121 | PULL IN: Date shift from 9/24 to 8/20, NCR created for flow controllers |  | Y |  |  | 67500 | BR Klees | Functional | Manual Valve | Shipped with Non-Conformance: 3/8” Manual Valve | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. | Yes | [6 empty] | Manual Valve | ENTEGRIS | 201-46-01-3 | HV064, HV065 | 2 | 2021-11-10 |  | TPC | 775166606362 | 5233 3984 0270 |  | 2021-11-15 | Yes | Installation Procedure for Entegris HV064 HV065_20210729 |  |  | Closed | I received valves 11/23/21. This tool is signed off, up and running with chemical. Need to work with customer on scheduled filter change out to install.
Q-19026 | Intel/Arizona | 5906010831 | 2021-05-13 | TPC | 4500099832 | 2021-08-20 | 486138 | 200445632 | 2 | EQ_ACDSys_LGD+B++_+NLG+++GC+++++FS_2++B | GX121 | PULL IN: Date shift from 9/24 to 8/20, NCR created for flow controllers |  | Y |  |  | 67697 | BR Klees | Functional | Flow Controller | Flow controller with same flow range but different port size – Need to investigate stock. Another potential is to just install 1 flow controller instead of 2. |  | Yes | [6 empty] | Flow Controller | ENTEGRIS | 6500-T6-F04-D12-K-P7-U3 (1.1) |  | 2 | 2022-02-18 |  | TPC |  |  | 776079943818 |  |  |  | 2021-11-02 |  | Closed | Customer Intel (Dan Lasley provided FC022 and FC026) Installed and tested for startup. FC022: S/N 36968 Flow: 0-5 L/min. Model: 6500-T6-F04-D12-K-P7-U3. FC026: S/N 38320 Flow: 0-5 L/min. Model: 6500-T6-F04-D12-K-P7-U3
Q-18803 | Intel/Oregon/D1X | 5906008483 | 2021-04-14 | TPC | 4500096943 | 2021-09-02 | 2309586 | 200445109 | 2 | EQ_ACDSys_LGDSB++_AML++++G++++++F+_2++A | XF051 | Tool ID name changed from HG051 to XF051 |  | Y |  |  | 67500 | BR Klees | Functional | Manual Valve | Shipped with Non-Conformance: 3/8” Manual Valve | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. | Yes | [6 empty] | Manual Valve | ENTEGRIS | 201-46-01-3 | HV064, HV065 | 2 | 2021-11-10 |  | TPC | 775049497664 | 523339839211 |  | 2021-11-04 | Yes | Installation Procedure for Entegris HV064 HV065_20210729 |  |  | Closed
Q-18803 | Intel/Oregon/D1X | 5906008483 | 2021-04-14 | TPC | 4500096943 | 2021-09-24 | 2305742 | 200445108 | 3 | EQ_ACDSys_LGDSB++_ANJ++++G++++++F+_2++A | RB051 | PUSH OUT: Date shift from 9/2 to 9/24 |  |  |  |  | 67500 | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Manual Valve | ENTEGRIS | 201-46-01-3 | HV064, HV065 | 2 | 2021-11-10 |  | TPC | 775166606362 | 5233 3984 0281 |  | 2021-11-15 | Yes | Installation Procedure for Entegris HV064 HV065_20210729 |  |  | Closed
Q-19027 | Intel/Arizona | 5906010831 LI 14 | 2021-05-19 | TPC | 4500101310 | 2021-09-24 | 488050 | 200445971 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++FS_2++A | VC121D | PULL IN: Date shift from 10/5 to 9/24 |  | N/A |  |  | 67500 | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Manual Valve | ENTEGRIS | 201-46-01-3 | HV064, HV065 | 2 | 2021-11-19 |  | TPC | 775245874285 | 5233 3984 2674 |  |  | Yes | Installation Procedure for Entegris HV064 HV065_20210729 | 2021-11-23 |  | Closed
Q-19027 | Intel/Arizona | 5906010831 LI 14 | 2021-05-19 | TPC | 4500101310 | 2021-09-24 | 488050 | 200445971 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++FS_2++A | VC121D | PULL IN: Date shift from 10/5 to 9/24 |  | N/A |  |  |  | BR Klees | Functional | Flow Controller | Flow controller unavailable by ship date. Test tool with Golden Tool FC, install FC in field. | Maintain shipment schedule |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Flow Controller | ENTEGRIS | 6500-T1-F02-D12-K-P7-U3 (1.1) |  | 1 | 2022-07-17 |  | TPC | [6 empty] | 2021-11-15 |  | Open | Customer Intel (Dan Lasley provided FC029) Installed and tested for startup. S/N 38881 Flow: 0-125 mL/min. Model: 6500-T1-F02-D12-K-P7-U3
Q-19027 | Intel/Arizona | 5906010831 LI 14 | 2021-05-19 | TPC | 4500101310 | 2021-09-24 | 488050 | 200445971 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++FS_2++A | VC121D | PULL IN: Date shift from 10/5 to 9/24 |  | N/A |  |  |  | BR Klees | Functional | HMI | Allen Bradley HMI deliver date shift to 9/30 | F series HMI expect to arrive TPC on end of September |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | HMI | Allen Bradley | 6181P-15A3SW71AC |  | 2 | 10/12/2021 |  | TPC |  | 523339837171 |  | 2021-10-25 | No |  | 2021-11-05 |  | Closed
Q-18189R3 | Intel/Oregon/D1X | 5906008483 | 2021-03-11 | TPC | 4500095621 | 2021-09-22 | 2305742 | 200444937 | 2 | EQ_ACDSys_LGDSB++_ANJ++++G++++++F+_2++A | CX051 | Enclosure is being built. |  | Y |  |  | 67500 | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 9/15/21 | BR 9/15/21 | RD 9/15/21 | BK 9/15/21 |  | Manual Valve | ENTEGRIS | 201-46-01-3 | HV064, HV065 | 2 | 2021-11-10 |  | TPC | 775049497664 | 523339839211 |  | 2021-11-04 | Yes | Installation Procedure for Entegris HV064 HV065_20210729 |  |  | Closed | 10/1 - FC location at FC021、FC025.(10/5)
Q-19028 | Intel/Arizona | 5906010831 LI 11 | 2021-05-19 | TPC | 4500101152 | 2021-10-29 | 486134 | 200445929 | 3 | EQ_ACDSys_LGD+B++_+NJ++++G++++++F+_2++A | FB122D | Updating MBOM for new filter vent option | [5 empty] | BR Klees | Functional | Flow Controller | Short flow controllers | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Flow Controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021、FC025 | 2 | 2022-01-07 |  | TPC |  |  | 775677367069 |  | Yes | NCSR Location List for FB122D_20211019 | 2021-12-06 |  | Closed | 10/1 - FC location at FC021、FC025.(10/5) FSE: RD - Intel has provided the FC'S. FC021 S/N: 39078 FLOW: 0-20 L/min. MODEL: 6501-T8-F06-D12-K-P7-U3-M36. FC025 S/N: 39087 FLOW: 0-20 L/min. MODEL: 6501-T8-F06-D12-K-P7-U3-M36. Received FC'S 1/12/22
Q-19028 | Intel/Arizona | 5906010831 LI 11 | 2021-05-19 | TPC | 4500101152 | 2021-10-29 | 486134 | 200445929 | 3 | EQ_ACDSys_LGD+B++_+NJ++++G++++++F+_2++A | FB122D | Updating MBOM for new filter vent option | [5 empty] | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Manual Valve | ENTEGRIS | 201-46-01-3 | FC021、FC025 | 2 | 2021-11-10 |  | TPC | 775166606362 | 5233 3984 0270 |  | 2021-11-15 | Yes | 2 items of NCSR location for LG-FB122D_20211101 |  |  | Closed | 10/1 - Does not match Jason's ist of deficient parts. Need to confirm. 10/5 --> Manual valve cantnot meet assembly schedule, therefore, shipped with NCSR; and will be sent to EMD after TPC arrives. Location at HV064、HV065.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Flow Controller | Short flow controllers | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Flow Controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021、FC025 | 2 | 2022-01-07 |  | TPC |  |  | 775677367069 |  |  |  | 2022-01-14 |  | Closed | 10/1 - Which FC? 10/5 FC location at FC121、FC221. | FSE: RD/EC Recieved and installed FC121 and FC221
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Filter Housing | Short filter housings | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Filter Housing | Pall | FPT10-3/4FL-1/4FL | FL101,FL102,FL201,FL202,FL021,FL022 | 6 | 2021-12-23 |  | TPC |  |  | 775574930022 |  |  |  | 2022-01-14 |  | Closed | 10/5 Location at FL101、FL102、FL201、FL202、FL021、FL022. | FSE: RD/EC Recieved and installed FL021,FL022, FL101,FL102, FL201, FL202.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Flow Controller | Short flow controllers | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Flow Controller | ENTEGRIS | 6500-T4-F03-D12-K-P7-U3 (1.1) |  | 1 | 2022-02-25 |  | TPC |  |  | 776139388676 | [5 empty] | Closed | 10/1 - Which FC location/ID? 10/5 FC location at FC122、FC222.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Flow Controller | Short flow controllers | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Flow Controller | ENTEGRIS | 6500-T4-F03-D12-K-P7-U3 (1.1) |  | 1 | 2022-02-25 |  | TPC |  |  | 776139388676 | [5 empty] | Closed | 10/1 - Which FC location/ID? 10/5 FC location at FC122、FC222.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Check Valve | Short check valves | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Check Valve | ENTEGRIS | CK8-8F-8F | KV003, KV004 | 2 | 2022-01-14 |  | TPC |  |  | 775738611140 | [5 empty] | Closed | 10/5 Location at KV003、KV004.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Particle Counter | Short particle counters | Will functionally test with in-house components and remove before shipment |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Particle Counter | PARTICLE MEASURING SYSTEM | 301070-0312 |  | 1 | 2012-02-11 |  | TPC |  |  | 775967704717 |  |  |  | 2022-02-11 |  | Closed | 10/1 - Allwiring/mechanical work completed? 10/5 The LPC cover has been installed. Location at LPC01. | 1/26/22 Intel provided Particle Counter and installed S/N 150395. Received NCSR Particle Counter on 2/11/22 and placed in Intel parts cage.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short Entegris filter venting valves | Intel requested to add filter venting function for future LG, the venting valve (Entegris , model 201-46-01-3, QTY: 2 per tool) lead time was shift from early August to October. The the tool functionality will be tested with substitute valves. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Manual Valve | ENTEGRIS | 201-97-01-3 |  | 2 | 2022-01-14 |  | TPC |  |  | 775738611140 |  |  | Installation Procedure for Entegris HV064 HV065_20210729 |  |  | Closed | 10/1 - Does this require a different procedure from the one shown in cell AQ? 10/5 The installation steps of HV025 and HV026 are different from the AQ field, and TPC will provide new installation instructions. Location at HV025、HV026.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Pressure Vessel | Short pressure vessel | Will use pressure vessels from KF112 for testing and shipment. Swap pressure vessels into KF112 in field. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Pressure Vessel | ENTEGRIS | 153-601-156 | VSL101 | 1 | 2022-04-26 |  | TPC |  |  | 776673564272 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/10%20items%20of%20NCSR%20location%20for%20CB-KF112_20220112.pdf | 2021-11-12 |  | Closed | 10/1 - Need some instruction from TPC to guide Robin's team on pressure vessel location and installation. 10/5 VSL installation instructions will be provided before the machine is released. Location at VSL101, VSL102 VSL201, VSL202. | FSE: RD/EC Recieved and installed VSL101,VSL102,VSL201,VSL202
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Pressure Vessel | Short pressure vessel | Will use pressure vessels from KF112 for testing and shipment. Swap pressure vessels into KF112 in field. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Pressure Vessel | ENTEGRIS | 153-601-156 | VSL102 | 1 | 2022-04-26 |  | TPC |  |  | 776673564272 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/10%20items%20of%20NCSR%20location%20for%20CB-KF112_20220112.pdf | 2021-11-12 |  | Closed
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Pressure Vessel | Short pressure vessel | Will use pressure vessels from KF112 for testing and shipment. Swap pressure vessels into KF112 in field. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Pressure Vessel | ENTEGRIS | 153-601-156 | VSL201 | 1 | 2022-04-26 |  | TPC |  |  | 776673564272 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/10%20items%20of%20NCSR%20location%20for%20CB-KF112_20220112.pdf | 2021-11-12 |  | Closed
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  | N/A |  | 2021-10-05 |  | BR Klees | Functional | Pressure Vessel | Short pressure vessel | Will use pressure vessels from KF112 for testing and shipment. Swap pressure vessels into KF112 in field. |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Pressure Vessel | ENTEGRIS | 153-601-156 | VSL202 | 1 | 2022-04-26 |  | TPC |  |  | 776673564272 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/10%20items%20of%20NCSR%20location%20for%20CB-KF112_20220112.pdf | 2021-11-12 |  | Closed
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 1 | 2021-12-17 |  | TPC |  |  | 775526366632 |  |  |  | 2022-01-14 |  | Closed | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage | FSE: RD/EC Recieved and installed HV021.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 1 | 2021-12-17 |  | TPC |  |  | 775526366632 |  |  |  | 2022-01-14 |  | Closed | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage | FSE: RD/EC Recieved and installed HV034.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 1 | 2021-12-17 |  | TPC |  |  | 775526366632 |  |  |  | 2022-01-14 |  | Closed | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage | FSE: RD/EC Recieved and installed HV124.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 1 | 2021-12-17 |  | TPC |  |  | 775526366632 |  |  |  | 2022-01-14 |  | Closed | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage | FSE: RD/EC Recieved and installed HV224.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 1 | 2021-12-17 |  | TPC |  |  | 775526366632 |  |  |  | 2022-01-14 |  | Closed | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage | FSE: RD/EC Recieved and installed HV126.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 1 | 2021-12-17 |  | TPC |  |  | 775526366632 |  |  |  | 2022-01-14 |  | Closed | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage | FSE: RD/EC Recieved and installed HV226.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 1 | 2022-01-14 |  | TPC |  |  | 775738611140 | [5 empty] | Closed | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | 201-42-01-3 | HV021、HV034、HV126、HV226 、HV124、HV224、 HV035、HV036 | 1 | 2022-01-14 |  | TPC |  |  | 775738611140 | [5 empty] | Closed | 10/6- Location at HV021、HV034、HV126、HV226 、HV124、HV224、HV035、HV036. --> Need to ship with NCSR due to shortage
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | Manual Valve | Short manual valves | Will functionally test with in-house components and remove before shipment | [7 empty] | Manual Valve | ENTEGRIS | DS12-2M-12F-3 | HV104. | 1 | 2022-02-18 |  | TPC |  |  | 776079821626 | [5 empty] | Closed | 10/5- Location at HV104.
Q-19024 | Intel/Arizona/F12 | 5906010831 LI 13 | 2021-05-19 | TPC | 4500101309 | 2021-10-14 | 2305744 | 200445967 | 4 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF112D | PULL IN: Date shift from 12/1 to 10/14 |  |  |  | 2021-10-05 |  | BR Klees | Functional | 3 way valve | Short 3-way valves | Will functionally test with in-house components and remove before shipment | [7 empty] | 3-Way Valve | ENTEGRIS | D8-3C-12F-3 | CV026、CV036、CV042 | 3 | 2022-01-07 |  | TPC |  |  | 775677367069 | Yes |  |  | 2022-01-14 |  | Closed | 10/5- Location at CV026、CV036、CV042. | FSE: RD/EC Recieved and installed CV026, CV036, CV042.
Q-19025 | Intel/Oregon/D1X | 5906010831 LI 12 | 2021-05-19 | TPC | 4500101309 | 2021-10-27 | 2305744 | 200445968 | 5 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | NX051 | PULL IN: Date shift from 12/1 to 10/27 |  | N/A |  |  |  | BR Klees | Functional | Flow Controller |  |  |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Flow Controller | ENTEGRIS | 6500-T4-F03-D12-K-P7-U3 (1.1) | FC122、FC222 | 1 | 2022-02-25 |  | TPC |  |  | 776139340557 |  | Yes | NX051 NCSR Location List |  |  | Closed | 10/1 - Location of FC's 10/5- FC location at FC122、FC222.
Q-19025 | Intel/Oregon/D1X | 5906010831 LI 12 | 2021-05-19 | TPC | 4500101309 | 2021-10-27 | 2305744 | 200445968 | 5 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | NX051 | PULL IN: Date shift from 12/1 to 10/27 |  | N/A |  |  |  | BR Klees | Functional | Flow Controller |  |  |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Flow Controller | ENTEGRIS | 6500-T4-F03-D12-K-P7-U3 (1.1) | FC122、FC222 | 1 | 2022-02-25 |  | TPC |  |  | 776139340557 |  | Yes | NX051 NCSR Location List |  |  | Closed | 10/1 - Location of FC's 10/5- FC location at FC122、FC222.
Q-19025 | Intel/Oregon/D1X | 5906010831 LI 12 | 2021-05-19 | TPC | 4500101309 | 2021-10-27 | 2305744 | 200445968 | 5 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | NX051 | PULL IN: Date shift from 12/1 to 10/27 |  | N/A |  |  |  | BR Klees | Functional | Filter Housing |  |  |  |  | JJ 10/1/21 | BR 10/1/21 | RD 10/1/21 | BK 10/1/21 |  | Filter Housing | Pall | FPT10-3/4FL-1/4FL | FL021、FL022 | 2 | 2021-11-19 |  | TPC | 775245874285 | 523339842674 |  |  | Yes | 2 items of NCSR location for CB-NX051_20211101 |  |  | Closed | 10/5- Location at FL021、FL022.
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Circuit Breaker | [9 empty] | Circuit Breaker | ALTECH/ Eaton | 3DU40L/ FAZ-D40-3-NA |  | 1 | 2021-12-03 |  | TPC |  |  | 775367137874 | 2021-12-03 |  |  |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Particle Counter | [9 empty] | Particle Counter | PARTICLE MEASURING SYSTEM | 301070-0512(FOR INTEL) (3.3 SP8) |  | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Flow Controller | [9 empty] | Flow Controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021、FC025 | 2 | 2022-01-07 |  | TPC |  |  | 775677385469 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Check Valve | [9 empty] | Check Valve | ENTEGRIS | CK8-8F-8F |  | 1 | 2022-01-14 |  | TPC |  |  | 775738434319 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Manual Valve | [9 empty] | Manual Valve | ENTEGRIS | DS12-2M-12F-3 |  | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Manual Valve | [9 empty] | Manual Valve | ENTEGRIS | DS12-2M-12F-3 |  | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Manual Valve | [9 empty] | Manual Valve | ENTEGRIS | DS12-2M-12F-3 |  | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Manual Valve | [9 empty] | 3-Way Valve | ENTEGRIS | D8-3C-12F-3 |  | 2 | 2022-02-08 |  | TPC |  |  | 775967694469 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Spray Gun | [9 empty] | Spray Gun | ENTEGRIS | 421-111-1 |  | 3 | 2022-02-18 |  | TPC |  |  | 776079837555 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Flow Controller | [9 empty] | Flow Controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC022 | 1 | 2022-04-14 |  | TPC |  |  | 776580056247 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | Flow Controller | Entegris | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC022, FC026 | 2 | 2022-04-08 | [6 empty] | Open | [5 empty] | Flow Controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC026 | 1 | 2022-04-14 |  | TPC |  |  | 776580056247 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | [18 empty] | Flow Controller | ENTEGRIS | 6500-T6-F04-D12-K-P7-U3 (1.1) | FC022 | 1 | 2022-06-22 |  | TPC |  |  | 777192581803 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 Line Item #070 | 2021-11-12 | 2311537 | 200449599 | 1 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | LW051 | C-22225, Intel requested on-site date is 11/18/2021 | [5 empty] | BR Klees | Functional | Flow Controller | [9 empty] | Flow Controller | ENTEGRIS | 6500-T6-F04-D12-K-P7-U3 (1.1) | FC026 | 1 | 2022-06-22 |  | TPC |  |  | 777192581803 | [5 empty] | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 010 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2021 | [5 empty] | BR Klees | Functional | Cable | [9 empty] | Cable | ENTEGRIS | 14G02 |  | 1 | 2021-12-23 |  | TPC |  |  | 775574975110 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2021 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Check Valve | ENTEGRIS | CK8-8F-8F | KV13 | 1 | 2022-01-14 |  | TPC |  |  | 775738434319 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2022 | [5 empty] | BR Klees | Functional | valves | [9 empty] | 3-Way Valve | ENTEGRIS | D8-3C-12F-3 | CV052 | 1 | 2022-02-08 |  | TPC |  |  | 775967694469 | Yes | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2023 | [5 empty] | BR Klees | Functional | transmitter | [9 empty] | 3-Way Valve | ENTEGRIS | D8-3C-12F-3 | CV011 | 1 | 2022-02-08 |  | TPC |  |  | 775967694469 | Yes | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2024 | [5 empty] | BR Klees | Functional | transmitter | [9 empty] | 3-Way Valve | ENTEGRIS | D8-3C-12F-3 | CV079 | 1 | 2022-02-08 |  | TPC |  |  | 775967694469 | Yes | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2025 | [5 empty] | BR Klees | Functional | transmitter | [9 empty] | 3-Way Valve | ENTEGRIS | D8-3C-12F-3 | NA | 1 | 2022-02-08 |  | TPC |  |  | 775967694469 | Yes | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2026 | [5 empty] | BR Klees | Functional | transmitter | [9 empty] | Transmitter | ENTEGRIS | 4400-T10-F08-D12-A-P7-U3 | FT001 | 1 | 2021-12-23 |  | TPC |  |  | 775574975110 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2027 | [5 empty] | BR Klees | Functional | Primelock | [9 empty] | Transmitter | ENTEGRIS | 4400-T10-F08-D12-A-P7-U3 | FT002 | 1 | 2021-12-23 |  | TPC |  |  | 775574975110 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2028 | [5 empty] | BR Klees | Functional | Primelock | [9 empty] | Transmitter | ENTEGRIS | 4400-T10-F08-D12-A-P7-U3 | FT014 | 1 | 2021-12-23 |  | TPC |  |  | 775574975110 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2029 | [5 empty] | BR Klees | Functional | Flow controller | [9 empty] | Transmitter | ENTEGRIS | 4400-T10-F08-D12-A-P7-U3 | FT001 | 1 | 2021-12-23 |  | TPC |  |  | 775574975110 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2030 | [5 empty] | BR Klees | Functional | Flow controller | [9 empty] | Primelock | ENTEGRIS | PP-16K16F-3MA |  | 1 | 2022-02-08 |  | TPC |  |  | 775967694469 | Yes | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2031 | [5 empty] | BR Klees | Functional | Flow controller | [9 empty] | Primelock | ENTEGRIS | PP-16K16F-3MA |  | 1 | 2022-02-08 |  | TPC |  |  | 775967694469 | Yes | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2032 | [5 empty] | BR Klees | Functional | Flow controller | [9 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021 | 1 | 2022-01-07 |  | TPC |  |  | 775677385469 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2033 | [5 empty] | BR Klees | Functional | spray gun | [9 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC025 | 1 | 2022-01-07 |  | TPC |  |  | 775677385469 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2034 | [5 empty] | BR Klees | Functional | spray gun | [9 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-04-14 |  | TPC |  |  | 776580056247 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2035 | [5 empty] | BR Klees | Functional | spray gun | [9 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-04-14 |  | TPC |  |  | 776580056247 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2036 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Spray Gun | ENTEGRIS | 421-111-1 | HG01 | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2037 | [5 empty] | BR Klees | Functional | Cable | [9 empty] | Spray Gun | ENTEGRIS | 421-111-1 | HG01 | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2038 | [5 empty] | BR Klees | Functional | LPC sensor | [9 empty] | Spray Gun | ENTEGRIS | 421-111-1 | HG02 | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2039 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Cable | PARTICLE MEASURING SYSTEM | PMS-CD1053 | NA | 1 | 2022-01-14 |  | TPC |  |  | 775738434319 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2040 | [5 empty] | BR Klees | Functional | valves | [9 empty] | LPC Sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC01 | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2041 | [5 empty] | BR Klees | Functional | valves | [9 empty] | LPC Sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC02 | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2042 | [5 empty] | BR Klees | Functional | Flow controller | [9 empty] | Manual Valve | ENTEGRIS | DS12-2M-12F-3 | HV015 | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2043 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Manual Valve | ENTEGRIS | DS12-2M-12F-3 | HV016 | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2044 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Manual Valve | ENTEGRIS | DS12-2M-12F-3 | HV011 | 1 | 2022-02-18 |  | TPC |  |  | 776079837555 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2045 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Flow controller | ENTEGRIS | 6500-T4-F04-D12-K-P7-U3 (1.1) | FC022 | 1 | 2022-08-02 |  | TPC |  |  | 777546287665 |  | See Columns AR/AU | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2046 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2047 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2048 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2049 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2049 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed | https://mdigital.sharepoint.com/:x:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/NCSR Location List for LY051_20211210.xlsx?d=wb8a0b98128294f358d8c5c5c3f1cc0da&csf=1&web=1&e=kz4FSG
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2049 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Manual Valve | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2021-12-03 |  | TPC |  |  | 775367137874 |  | No | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 009 | 2021-08-10 | TPC | 4500111773 #010 | 2021-11-29 | 2311533 | 200449593 | 1 | EQ_ACDSys_LGD+B++_SNJE+++GC+++++F+_2++B | LY051 | C-22227, Intel requested on-site date is 11/29/2021, Date shift from 11/22/2021 to 11/29/2049 | [5 empty] | BR Klees | Functional | valves | [9 empty] | Manual Valve | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2021-12-03 |  | TPC |  |  | 775367137874 |  | No | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/14%20items%20of%20NCSR%20location%20for%20LG-LY051%20_20220426.pdf |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A |  |  | N/A | [15 empty] | Valves | CLIPPARD | 2012 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Valves | CLIPPARD | 2012 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Valves | CLIPPARD | 2012 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Valves | CLIPPARD | 2012 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Fitting | CLIPPARD | 15080 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Fitting | CLIPPARD | 15080 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Fitting | CLIPPARD | 15080 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Fitting | CLIPPARD | 15080 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Piping | PARKER | P4MT2 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Piping | PARKER | P4MT2 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Piping | PARKER | P4MT2 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Piping | PARKER | P4MT2 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Piping | PARKER | P4MT2 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Piping | PARKER | P4MT2 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Q-16820 | Micron/Manassas/VA | 4510054178 | 2021-05-14 | TPC | 4500102886 | 2021-12-10 | 2310904 | 200446156 | 1 | EQ_PCSys_TyphoonS790_ND++A+++++++++ | N/A | [18 empty] | Piping | PARKER | P4MT2 |  | 1 | 2022-01-27 |  | TPC |  |  | 775871589971 |  | Yes | Valve Install |  |  | Closed
Not Quoted | Intel/Ireland/F24 | 4200227600 | 2021-07-14 | TPC | 4500106436 Line Item #020 | 2021-12-17 | 487982 | 200447275 | 15 | EQ_PCSys_Sink1087_+++++++ | PCU301 | Intel requested date is 1/6/2022, Intel PO price is wrong: $1,246,300 | [17 empty] | Pressure Swtich | Z_BARKSDALE CONTROLS DIVISION | E1S-H90-PLS-E1) | PS-1 | 1 | 2022-02-18 |  | TPC |  |  | 776079873428 |  | Yes | NCSR Location List for S1087-PCU301_20211215.xlsx |  |  | Closed
Not Quoted | Intel/Ireland/F24 | 4200227600 | 2021-07-14 | TPC | 4500106436 | 2021-12-17 | 487982 | 200447275 | 15 | EQ_PCSys_Sink1087_+++++++ | PCU301 | Intel requested date is 1/6/2022, Intel PO price is wrong: $1,246,300 | [17 empty] | Pressure Swtich | Z_BARKSDALE CONTROLS DIVISION | E1S-H90-PLS-E1) | PS-2 | 1 | 2022-02-18 |  | TPC |  |  | 776079873428 |  | Yes | 1 items of NCSR location for S1087-PCU301 _20211215.pptx |  |  | Closed
Q-19441 | Intel/Oregon/D1D | 4200230516 | 2021-08-02 | TPC | 4500107589 | 2021-12-17 | 487982 | 200447675 | 20 | EQ_PCSys_Sink1087_+++++++ | PCU419 | [18 empty] | Pressure Swtich | Z_BARKSDALE CONTROLS DIVISION | E1S-H90-PLS-E1) | PS-1 | 1 | 2022-02-18 |  | TPC |  |  | 776080075076 |  | Yes | NCSR Location List for S1087-PCU419_20211215.xlsx |  |  | Closed
Q-19441 | Intel/Oregon/D1D | 4200230516 | 2021-08-02 | TPC | 4500107589 | 2021-12-17 | 487982 | 200447675 | 20 | EQ_PCSys_Sink1087_+++++++ | PCU419 | [18 empty] | Pressure Swtich | Z_BARKSDALE CONTROLS DIVISION | E1S-H90-PLS-E1) | PS-2 | 1 | 2022-02-18 |  | TPC |  |  | 776080075076 |  | Yes | 1 items of NCSR location for S1087-PCU419 _20211215.pptx |  |  | Closed
Not Quoted | Intel/Ireland/F24 | 4200227598 | 2021-07-14 | TPC | 4500106436 Line Item #030 | 2022-01-14 | 487982 | 200447276 | 16 | EQ_PCSys_Sink1087_+++++++ | PCU302 | [18 empty] | Pressure Swtich | Z_BARKSDALE CONTROLS DIVISION | E1S-H90-PLS-E1) | PS-1 | 1 | 2022-02-18 |  | TPC |  |  | 776079873428 | [5 empty] | Closed
Not Quoted | Intel/Ireland/F24 | 4200227598 | 2021-07-14 | TPC | 4500106436 Line Item #030 | 2022-01-14 | 487982 | 200447276 | 16 | EQ_PCSys_Sink1087_+++++++ | PCU302 | [18 empty] | Pressure Swtich | Z_BARKSDALE CONTROLS DIVISION | E1S-H90-PLS-E1) | PS-2 | 1 | 2022-02-18 |  | TPC |  |  | 776079873428 | [5 empty] | Closed
Not Quoted | Intel/Ireland/F24 | 4200227598 | 2021-07-14 | TPC | 4500106436 Line Item #030 | 2022-01-14 | 487982 | 200447276 | 16 | EQ_PCSys_Sink1087_+++++++ | PCU302 | [18 empty] | spray gun | ENTEGRIS | 421-111-1 | NA | 1 | 2022-02-18 |  | TPC |  |  | 776079873428 | [5 empty] | Closed
Not Quoted | Intel/Ireland/F24 | 4200227604 | 2021-07-14 | TPC | 4500106645 line item 010 | 2022-02-11 | 2304792 | 200447281 | 1 | EQ_PCSys_Sink1088_+S+++++ | SNK707 | Intel requested date is 3/14/2022 |  | N/A | [15 empty] | Pressure Swtich | Z_BARKSDALE CONTROLS DIVISION | E1S-H90-PLS-E1) | 4SWI10000127 | 1 | 2022-02-18 |  | TPC |  |  | 776079873428 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/Replacement%20Procedure%20of%20Pressure%20Switch%20Cover%20for%20S1088-SNK707_20220126.pptx?d=wad1239f3b1b24626bbc463653b827c67 |  |  | Closed
Not Quoted | Intel/Ireland/F24 | 4200227604 | 2021-07-14 | TPC | 4500106645 line item 010 | 2022-02-11 | 2304792 | 200447281 | 1 | EQ_PCSys_Sink1088_+S+++++ | SNK707 | Intel requested date is 3/14/2022 |  | N/A | [15 empty] | Pressure Swtich | Z_BARKSDALE CONTROLS DIVISION | E1S-H90-PLS-E1) | 4SWI10000127 | 1 | 2022-02-18 |  | TPC |  |  | 776079873428 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/Replacement%20Procedure%20of%20Pressure%20Switch%20Cover%20for%20S1088-SNK707_20220126.pptx?d=wad1239f3b1b24626bbc463653b827c67 |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 013 | 2021-08-16 | TPC | 4500111773 Line Item #050 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 013 | 2021-08-16 | TPC | 4500111773 Line Item #050 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod4 | 5906010199, line item 014 | 2021-08-17 | TPC | 4500111773 Line Item #051 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod5 | 5906010199, line item 015 | 2021-08-18 | TPC | 4500111773 Line Item #052 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021 | 1 | 2022-04-08 |  | TPC |  |  | 776525720068 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC025 | 1 | 2022-04-08 |  | TPC |  |  | 776525720068 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Flow controller | ENTEGRIS | 6500-T3-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-10-17 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Flow controller | ENTEGRIS | 6500-T3-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-10-17 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-12-12 |  | TPC |  |  | 770756346718 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL02 | 1 | 2022-12-12 |  | TPC |  |  | 770756346718 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL03 | 1 | 2022-12-12 |  | TPC |  |  | 770756346718 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL04 | 1 | 2022-12-12 |  | TPC |  |  | 770756346718 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV008 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV009 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 016 | 2021-08-19 | TPC | 4500111773 Line Item #053 | 2022-03-24 | 2311536 | 200449597 | 2 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | EW051 | C-22224, Intel requested on-site date is 12/27/2021, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20EW051_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 012 | 2021-08-12 | TPC | 4500111773 Line Item #060 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19481 | Intel/Oregon/D1X-Mod4 | 5906010199, line item 013 | 2021-08-13 | TPC | 4500111773 Line Item #061 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19482 | Intel/Oregon/D1X-Mod5 | 5906010199, line item 014 | 2021-08-14 | TPC | 4500111773 Line Item #062 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19483 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 015 | 2021-08-15 | TPC | 4500111773 Line Item #063 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19484 | Intel/Oregon/D1X-Mod7 | 5906010199, line item 016 | 2021-08-16 | TPC | 4500111773 Line Item #064 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19485 | Intel/Oregon/D1X-Mod8 | 5906010199, line item 017 | 2021-08-17 | TPC | 4500111773 Line Item #065 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19486 | Intel/Oregon/D1X-Mod9 | 5906010199, line item 018 | 2021-08-18 | TPC | 4500111773 Line Item #066 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021 | 1 | 2022-04-08 |  | TPC |  |  | 776525720068 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19487 | Intel/Oregon/D1X-Mod10 | 5906010199, line item 019 | 2021-08-19 | TPC | 4500111773 Line Item #067 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC025 | 1 | 2022-04-08 |  | TPC |  |  | 776525720068 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19488 | Intel/Oregon/D1X-Mod11 | 5906010199, line item 020 | 2021-08-20 | TPC | 4500111773 Line Item #068 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-12-12 |  | TPC |  |  | 770756346718 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19489 | Intel/Oregon/D1X-Mod12 | 5906010199, line item 021 | 2021-08-21 | TPC | 4500111773 Line Item #069 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL02 | 1 | 2022-12-12 |  | TPC |  |  | 770756346718 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19490 | Intel/Oregon/D1X-Mod13 | 5906010199, line item 022 | 2021-08-22 | TPC | 4500111773 Line Item #070 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL03 | 1 | 2022-12-12 |  | TPC |  |  | 770756346718 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19491 | Intel/Oregon/D1X-Mod14 | 5906010199, line item 023 | 2021-08-23 | TPC | 4500111773 Line Item #071 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL04 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Open
Q-19492 | Intel/Oregon/D1X-Mod15 | 5906010199, line item 024 | 2021-08-24 | TPC | 4500111773 Line Item #072 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Open
Q-19493 | Intel/Oregon/D1X-Mod16 | 5906010199, line item 025 | 2021-08-25 | TPC | 4500111773 Line Item #073 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV008 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19494 | Intel/Oregon/D1X-Mod17 | 5906010199, line item 026 | 2021-08-26 | TPC | 4500111773 Line Item #074 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV009 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19495 | Intel/Oregon/D1X-Mod18 | 5906010199, line item 027 | 2021-08-27 | TPC | 4500111773 Line Item #075 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19496 | Intel/Oregon/D1X-Mod19 | 5906010199, line item 028 | 2021-08-28 | TPC | 4500111773 Line Item #076 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19497 | Intel/Oregon/D1X-Mod20 | 5906010199, line item 029 | 2021-08-29 | TPC | 4500111773 Line Item #077 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19498 | Intel/Oregon/D1X-Mod21 | 5906010199, line item 030 | 2021-08-30 | TPC | 4500111773 Line Item #078 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19499 | Intel/Oregon/D1X-Mod22 | 5906010199, line item 031 | 2021-08-31 | TPC | 4500111773 Line Item #079 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19500 | Intel/Oregon/D1X-Mod23 | 5906010199, line item 032 | 2021-09-01 | TPC | 4500111773 Line Item #080 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19501 | Intel/Oregon/D1X-Mod24 | 5906010199, line item 033 | 2021-09-02 | TPC | 4500111773 Line Item #081 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19502 | Intel/Oregon/D1X-Mod25 | 5906010199, line item 034 | 2021-09-03 | TPC | 4500111773 Line Item #082 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19503 | Intel/Oregon/D1X-Mod26 | 5906010199, line item 035 | 2021-09-04 | TPC | 4500111773 Line Item #083 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19504 | Intel/Oregon/D1X-Mod27 | 5906010199, line item 036 | 2021-09-05 | TPC | 4500111773 Line Item #084 | 2022-03-24 | 2311536 | 200449598 | 3 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | RV041 | C-22224, Intel requested on-site date is 12/29/2021, Name change to RV041, Original Ship Date: 1/14/2022, Parts Delay leading to the 5/13/2022 new date |  | N/A | [15 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20LG%20RV041_20220506.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | [18 empty] | USB Cable | LIMNDY | 4CM310 | USB CABLE | 1 | NA | [6 empty] | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC025 | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-10-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL02 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL03 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL04 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV008 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV009 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-06-15 |  | TPC |  |  | 777131415646 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-06-15 |  | TPC |  |  | 777131415646 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-06-15 |  | TPC |  |  | 777131415646 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-06-15 |  | TPC |  |  | 777131415646 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-06-15 |  | TPC |  |  | 777131415646 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-06-15 |  | TPC |  |  | 777131415646 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-07-26 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-07-26 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Flow controller | ENTEGRIS | 6500-T4-F04-D12-K-P7-U3 (1.1) | FC022 | 1 | 2022-08-02 |  | TPC |  |  | 777546287665 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Flow controller | ENTEGRIS | 6500-T4-F04-D12-K-P7-U3 (1.1) | FC026 | 1 | 2022-08-02 |  | TPC |  |  | 777546287665 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02, 05 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | Analysis | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC02 | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV001 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV003 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV057 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV058 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV059 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV042 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV043 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV039 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV046 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV040 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV025 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV026 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV041 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV070 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 007 | 2021-08-10 | TPC | 4500111773 Line Item #020 | 2022-04-13 | 2311534 | 200449594 | 1 | EQ_ACDSys_LGD+B++_SNJD+++GC+++++F+_2++B | JX051 | C-22228 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV055 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open | [5 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL02 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL03 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL04 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | Filter Housing | ENTEGRIS | YY6620A2FE | FL04 | 1 | 2022-10-27 |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open | [5 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-10-27 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV008 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV009 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-05-12 |  | TPC |  |  | 776837775890 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-05-26 |  | TPC |  |  | 776963228505 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Flow controller | ENTEGRIS | 6500-T3-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-10-17 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Flow controller | ENTEGRIS | 6500-T3-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-10-17 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Open
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC022 | 1 | 2022-07-08 |  | TPC |  |  | 777332757388 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC026 | 1 | 2022-07-08 |  | TPC |  |  | 777332757388 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02, 05 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 006 | 2021-08-10 | TPC | 4500111773 Line Item #040 | 2022-04-13 | 2311536 | 200449596 | 1 | EQ_ACDSys_LGD+B++_SNKF+++GC+++++F+_2++B | GN051 | C-22224 | [17 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Not Quoted | Intel/Ireland/F24 | 4200227602 | 2021-07-14 | TPC | 4500106436 Line Item #050 | 2022-04-19 | 487982 | 200447279 | 18 | EQ_PCSys_Sink1087_+++++++ | PCU802 | [18 empty] | valves | ENTEGRIS | 203-1414-215 | SV-1 | 1 | 2022-05-05 |  | TPC |  |  | 576169104208 |  | Yes | https://mdigital.sharepoint.com/:p:/r/sites/dsspolyflow-tpc/Shared Documents/Parts shortage issue/NCSR information from tpc/1 items of NCSR location for S1087-PCU802 _20220415.pptx?d=w31b5be82a1f0437a96cf9e315de6382e&csf=1&web=1&e=x4mvWJ |  |  | Open
Q-19568 rev 2 | Intel/Ireland/F24 | 4200233555 | 2021-08-19 | Apex | 4500107422 line item 030 | 2022-05-27 | 2305757 | 200447620 | 6 | EQ_PCSys_S1702_Universal_LL++++ | NAB701 | [18 empty] | Regulator | RK Industries | FPR-1003K-32MM | RG-1 | 1 | 2022-06-23 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Tool shipping complete
Q-19568 rev 2 | Intel/Ireland/F24 | 4200233555 | 2021-08-19 | Apex | 4500107422 line item 030 | 2022-05-27 | 2305757 | 200447620 | 6 | EQ_PCSys_S1702_Universal_LL++++ | NAB701 | [18 empty] | Regulator | RK Industries | FPR-1003K-32MM | RG-5 | 1 | 2022-06-23 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Tool shipping complete
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | PULL IN: Date shift from 12/1 to 10/27, Tool ID Change to NX051 | [17 empty] | Vessel Pressure | ENTEGRIS | 153-601-156 | VSL201 | 1 | 2022-08-17 |  | TPC |  |  | 777668093629 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Vessel Pressure | ENTEGRIS | 153-601-156 | VSL202 | 1 | 2022-08-17 |  | TPC |  |  | 777668093629 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Vessel Pressure | ENTEGRIS | 153-601-156 | VSL101 | 1 | 2022-08-17 |  | TPC |  |  | 777668093629 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Vessel Pressure | ENTEGRIS | 153-601-156 | VSL102 | 1 | 2022-08-17 |  | TPC |  |  | 777668093629 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Filter | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL201 | 1 | 2022-07-13 |  | TPC |  |  | 777370414035 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Filter | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL202 | 1 | 2022-07-13 |  | TPC |  |  | 777370414035 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Filter | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL101 | 1 | 2022-07-13 |  | TPC |  |  | 777370414035 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Filter | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL102 | 1 | 2022-07-13 |  | TPC |  |  | 777370414035 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Filter | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL021 | 1 | 2022-07-13 |  | TPC |  |  | 777370414035 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | Filter | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL022 | 1 | 2022-07-13 |  | TPC |  |  | 777370414035 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV107 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV108 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV109 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV110 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV104 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV113 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV204 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV207 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV208 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV209 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV210 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV213 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV114 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV214 | 1 | 2022-06-22 |  | TPC |  |  | 777192555118 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV028 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV103 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV203 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV116 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV216 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV005 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV102 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV202 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV047 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV044 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV045 | 1 | 2022-08-30 |  | TPC |  |  | 777782179039 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV027 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV111 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV112 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV023 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV032 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV212 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV211 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV219 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19025 | Intel/Arizona/F32 | 5906010831 LI 12 | 2021-05-19 | TPC | 4500115370 | 2022-05-24 | 2305744 | 200451076 | 6 | EQ_ACDSys_CBHDNG+++D++A+++_ARDSVBDFLBS+ | KF122 | [18 empty] | valves | ENTEGRIS | 202-179-01-3 | CV024 | 1 | 2022-06-01 |  | TPC |  |  | 776992585594 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/5%20items%20of%20NCSR%20location%20for%20KF122_20220606.pdf?csf=1&web=1 |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 011 | 2021-08-10 | TPC | 4500111773 Line Item #080 | 2022-06-22 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV001 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19481 | Intel/Oregon/D1X-Mod4 | 5906010199, line item 012 | 2021-08-11 | TPC | 4500111773 Line Item #081 | 2022-06-23 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV003 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19482 | Intel/Oregon/D1X-Mod5 | 5906010199, line item 013 | 2021-08-12 | TPC | 4500111773 Line Item #082 | 2022-06-24 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV057 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19483 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 014 | 2021-08-13 | TPC | 4500111773 Line Item #083 | 2022-06-25 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV058 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19484 | Intel/Oregon/D1X-Mod7 | 5906010199, line item 015 | 2021-08-14 | TPC | 4500111773 Line Item #084 | 2022-06-26 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV059 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19485 | Intel/Oregon/D1X-Mod8 | 5906010199, line item 016 | 2021-08-15 | TPC | 4500111773 Line Item #085 | 2022-06-27 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV071 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19486 | Intel/Oregon/D1X-Mod9 | 5906010199, line item 017 | 2021-08-16 | TPC | 4500111773 Line Item #086 | 2022-06-28 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV042 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19487 | Intel/Oregon/D1X-Mod10 | 5906010199, line item 018 | 2021-08-17 | TPC | 4500111773 Line Item #087 | 2022-06-29 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV043 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19488 | Intel/Oregon/D1X-Mod11 | 5906010199, line item 019 | 2021-08-18 | TPC | 4500111773 Line Item #088 | 2022-06-30 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV039 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19489 | Intel/Oregon/D1X-Mod12 | 5906010199, line item 020 | 2021-08-19 | TPC | 4500111773 Line Item #089 | 2022-07-01 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV046 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19490 | Intel/Oregon/D1X-Mod13 | 5906010199, line item 021 | 2021-08-20 | TPC | 4500111773 Line Item #090 | 2022-07-02 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV040 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19491 | Intel/Oregon/D1X-Mod14 | 5906010199, line item 022 | 2021-08-21 | TPC | 4500111773 Line Item #091 | 2022-07-03 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV025 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19492 | Intel/Oregon/D1X-Mod15 | 5906010199, line item 023 | 2021-08-22 | TPC | 4500111773 Line Item #092 | 2022-07-04 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV026 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19493 | Intel/Oregon/D1X-Mod16 | 5906010199, line item 024 | 2021-08-23 | TPC | 4500111773 Line Item #093 | 2022-07-05 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV041 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19494 | Intel/Oregon/D1X-Mod17 | 5906010199, line item 025 | 2021-08-24 | TPC | 4500111773 Line Item #094 | 2022-07-06 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV070 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19495 | Intel/Oregon/D1X-Mod18 | 5906010199, line item 026 | 2021-08-25 | TPC | 4500111773 Line Item #095 | 2022-07-07 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV055 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19496 | Intel/Oregon/D1X-Mod19 | 5906010199, line item 027 | 2021-08-26 | TPC | 4500111773 Line Item #096 | 2022-07-08 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Open
Q-19497 | Intel/Oregon/D1X-Mod20 | 5906010199, line item 028 | 2021-08-27 | TPC | 4500111773 Line Item #097 | 2022-07-09 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL02 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Open
Q-19498 | Intel/Oregon/D1X-Mod21 | 5906010199, line item 029 | 2021-08-28 | TPC | 4500111773 Line Item #098 | 2022-07-10 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL03 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Open
Q-19499 | Intel/Oregon/D1X-Mod22 | 5906010199, line item 030 | 2021-08-29 | TPC | 4500111773 Line Item #099 | 2022-07-11 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL04 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Open
Q-19500 | Intel/Oregon/D1X-Mod23 | 5906010199, line item 031 | 2021-08-30 | TPC | 4500111773 Line Item #100 | 2022-07-12 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Open
Q-19501 | Intel/Oregon/D1X-Mod24 | 5906010199, line item 032 | 2021-08-31 | TPC | 4500111773 Line Item #101 | 2022-07-13 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19502 | Intel/Oregon/D1X-Mod25 | 5906010199, line item 033 | 2021-09-01 | TPC | 4500111773 Line Item #102 | 2022-07-14 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19503 | Intel/Oregon/D1X-Mod26 | 5906010199, line item 034 | 2021-09-02 | TPC | 4500111773 Line Item #103 | 2022-07-15 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19504 | Intel/Oregon/D1X-Mod27 | 5906010199, line item 035 | 2021-09-03 | TPC | 4500111773 Line Item #104 | 2022-07-16 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19505 | Intel/Oregon/D1X-Mod28 | 5906010199, line item 036 | 2021-09-04 | TPC | 4500111773 Line Item #105 | 2022-07-17 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19506 | Intel/Oregon/D1X-Mod29 | 5906010199, line item 037 | 2021-09-05 | TPC | 4500111773 Line Item #106 | 2022-07-18 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-19507 | Intel/Oregon/D1X-Mod30 | 5906010199, line item 038 | 2021-09-06 | TPC | 4500111773 Line Item #107 | 2022-07-19 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19508 | Intel/Oregon/D1X-Mod31 | 5906010199, line item 039 | 2021-09-07 | TPC | 4500111773 Line Item #108 | 2022-07-20 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02, 05 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19509 | Intel/Oregon/D1X-Mod32 | 5906010199, line item 040 | 2021-09-08 | TPC | 4500111773 Line Item #109 | 2022-07-21 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19510 | Intel/Oregon/D1X-Mod33 | 5906010199, line item 041 | 2021-09-09 | TPC | 4500111773 Line Item #110 | 2022-07-22 | 2311537 | 200449600 | 2 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | JV051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/4%20items%20of%20NCSR%20location%20for%20LG%20JV051_20220623.pdf |  |  | Closed
Q-19480 | Intel/Oregon/D1X-Mod3 | 5906010199, line item 008 | 2021-08-10 | TPC | 4500111773 Line Item #030 | 2022-06-22 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV001 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19481 | Intel/Oregon/D1X-Mod4 | 5906010199, line item 009 | 2021-08-11 | TPC | 4500111773 Line Item #031 | 2022-06-23 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV003 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19482 | Intel/Oregon/D1X-Mod5 | 5906010199, line item 010 | 2021-08-12 | TPC | 4500111773 Line Item #032 | 2022-06-24 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV057 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19483 | Intel/Oregon/D1X-Mod6 | 5906010199, line item 011 | 2021-08-13 | TPC | 4500111773 Line Item #033 | 2022-06-25 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV058 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19484 | Intel/Oregon/D1X-Mod7 | 5906010199, line item 012 | 2021-08-14 | TPC | 4500111773 Line Item #034 | 2022-06-26 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV059 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19485 | Intel/Oregon/D1X-Mod8 | 5906010199, line item 013 | 2021-08-15 | TPC | 4500111773 Line Item #035 | 2022-06-27 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV071 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19486 | Intel/Oregon/D1X-Mod9 | 5906010199, line item 014 | 2021-08-16 | TPC | 4500111773 Line Item #036 | 2022-06-28 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV042 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19487 | Intel/Oregon/D1X-Mod10 | 5906010199, line item 015 | 2021-08-17 | TPC | 4500111773 Line Item #037 | 2022-06-29 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV043 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19488 | Intel/Oregon/D1X-Mod11 | 5906010199, line item 016 | 2021-08-18 | TPC | 4500111773 Line Item #038 | 2022-06-30 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV039 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19489 | Intel/Oregon/D1X-Mod12 | 5906010199, line item 017 | 2021-08-19 | TPC | 4500111773 Line Item #039 | 2022-07-01 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV046 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19490 | Intel/Oregon/D1X-Mod13 | 5906010199, line item 018 | 2021-08-20 | TPC | 4500111773 Line Item #040 | 2022-07-02 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV040 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19491 | Intel/Oregon/D1X-Mod14 | 5906010199, line item 019 | 2021-08-21 | TPC | 4500111773 Line Item #041 | 2022-07-03 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV025 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19492 | Intel/Oregon/D1X-Mod15 | 5906010199, line item 020 | 2021-08-22 | TPC | 4500111773 Line Item #042 | 2022-07-04 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV026 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19493 | Intel/Oregon/D1X-Mod16 | 5906010199, line item 021 | 2021-08-23 | TPC | 4500111773 Line Item #043 | 2022-07-05 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV041 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19494 | Intel/Oregon/D1X-Mod17 | 5906010199, line item 022 | 2021-08-24 | TPC | 4500111773 Line Item #044 | 2022-07-06 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV070 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19495 | Intel/Oregon/D1X-Mod18 | 5906010199, line item 023 | 2021-08-25 | TPC | 4500111773 Line Item #045 | 2022-07-07 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV055 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19496 | Intel/Oregon/D1X-Mod19 | 5906010199, line item 024 | 2021-08-26 | TPC | 4500111773 Line Item #046 | 2022-07-08 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19497 | Intel/Oregon/D1X-Mod20 | 5906010199, line item 025 | 2021-08-27 | TPC | 4500111773 Line Item #047 | 2022-07-09 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL02 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19498 | Intel/Oregon/D1X-Mod21 | 5906010199, line item 026 | 2021-08-28 | TPC | 4500111773 Line Item #048 | 2022-07-10 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL03 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19499 | Intel/Oregon/D1X-Mod22 | 5906010199, line item 027 | 2021-08-29 | TPC | 4500111773 Line Item #049 | 2022-07-11 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL04 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19500 | Intel/Oregon/D1X-Mod23 | 5906010199, line item 028 | 2021-08-30 | TPC | 4500111773 Line Item #050 | 2022-07-12 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Filter Housing | ENTEGRIS | YY6620A2FE | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19501 | Intel/Oregon/D1X-Mod24 | 5906010199, line item 029 | 2021-08-31 | TPC | 4500111773 Line Item #051 | 2022-07-13 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19502 | Intel/Oregon/D1X-Mod25 | 5906010199, line item 030 | 2021-09-01 | TPC | 4500111773 Line Item #052 | 2022-07-14 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19503 | Intel/Oregon/D1X-Mod26 | 5906010199, line item 031 | 2021-09-02 | TPC | 4500111773 Line Item #053 | 2022-07-15 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19504 | Intel/Oregon/D1X-Mod27 | 5906010199, line item 032 | 2021-09-03 | TPC | 4500111773 Line Item #054 | 2022-07-16 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19505 | Intel/Oregon/D1X-Mod28 | 5906010199, line item 033 | 2021-09-04 | TPC | 4500111773 Line Item #055 | 2022-07-17 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19506 | Intel/Oregon/D1X-Mod29 | 5906010199, line item 034 | 2021-09-05 | TPC | 4500111773 Line Item #056 | 2022-07-18 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19507 | Intel/Oregon/D1X-Mod30 | 5906010199, line item 035 | 2021-09-06 | TPC | 4500111773 Line Item #057 | 2022-07-19 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19507 | Intel/Oregon/D1X-Mod30 | 5906010199, line item 035 | 2021-09-06 | TPC | 4500111773 Line Item #057 | 2022-07-19 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-25 | [6 empty] | Open | [5 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02, 05 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19508 | Intel/Oregon/D1X-Mod31 | 5906010199, line item 036 | 2021-09-07 | TPC | 4500111773 Line Item #058 | 2022-07-20 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19509 | Intel/Oregon/D1X-Mod32 | 5906010199, line item 037 | 2021-09-08 | TPC | 4500111773 Line Item #059 | 2022-07-21 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19511 | Intel/Oregon/D1X-Mod34 | 5906010199, line item 039 | 2021-09-10 | TPC | 4500111773 Line Item #061 | 2022-07-23 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19512 | Intel/Oregon/D1X-Mod35 | 5906010199, line item 040 | 2021-09-11 | TPC | 4500111773 Line Item #062 | 2022-07-24 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Closed
Q-19513 | Intel/Oregon/D1X-Mod36 | 5906010199, line item 041 | 2021-09-12 | TPC | 4500111773 Line Item #063 | 2022-07-25 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-07-26 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-19514 | Intel/Oregon/D1X-Mod37 | 5906010199, line item 042 | 2021-09-13 | TPC | 4500111773 Line Item #064 | 2022-07-26 | 2311535 | 200449595 | 1 | EQ_ACDSys_LGD+B++_SNMD+++GC+++++F+_2++B | CD051 | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-07-26 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG%20CD051_20220623.pdf?csf=1&web=1 |  |  | Open
Q-20206 | Intel/Oregon/D1X | 5906010199 | 2021-12-09 | TPC | 4500129018 line item 010 | 2022-07-08 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-20207 | Intel/Oregon/D1X | 5906010200 | 2021-12-10 | TPC | 4500129018 line item 011 | 2022-07-09 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-20208 | Intel/Oregon/D1X | 5906010201 | 2021-12-11 | TPC | 4500129018 line item 012 | 2022-07-10 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-20209 | Intel/Oregon/D1X | 5906010202 | 2021-12-12 | TPC | 4500129018 line item 013 | 2022-07-11 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-20210 | Intel/Oregon/D1X | 5906010203 | 2021-12-13 | TPC | 4500129018 line item 014 | 2022-07-12 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-20211 | Intel/Oregon/D1X | 5906010204 | 2021-12-14 | TPC | 4500129018 line item 015 | 2022-07-13 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/7%20items%20of%20NCSR%20location%20for%20LG%20GN051_20220509.pdf |  |  | Closed
Q-20212 | Intel/Oregon/D1X | 5906010205 | 2021-12-15 | TPC | 4500129018 line item 016 | 2022-07-14 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV001 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20213 | Intel/Oregon/D1X | 5906010206 | 2021-12-16 | TPC | 4500129018 line item 017 | 2022-07-15 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV003 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20214 | Intel/Oregon/D1X | 5906010207 | 2021-12-17 | TPC | 4500129018 line item 018 | 2022-07-16 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-12-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Open
Q-20215 | Intel/Oregon/D1X | 5906010208 | 2021-12-18 | TPC | 4500129018 line item 019 | 2022-07-17 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV057 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20216 | Intel/Oregon/D1X | 5906010209 | 2021-12-19 | TPC | 4500129018 line item 020 | 2022-07-18 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV058 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20217 | Intel/Oregon/D1X | 5906010210 | 2021-12-20 | TPC | 4500129018 line item 021 | 2022-07-19 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV059 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20218 | Intel/Oregon/D1X | 5906010211 | 2021-12-21 | TPC | 4500129018 line item 022 | 2022-07-20 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV071 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20219 | Intel/Oregon/D1X | 5906010212 | 2021-12-22 | TPC | 4500129018 line item 023 | 2022-07-21 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV042 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20220 | Intel/Oregon/D1X | 5906010213 | 2021-12-23 | TPC | 4500129018 line item 024 | 2022-07-22 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV043 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20221 | Intel/Oregon/D1X | 5906010214 | 2021-12-24 | TPC | 4500129018 line item 025 | 2022-07-23 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV039 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20222 | Intel/Oregon/D1X | 5906010215 | 2021-12-25 | TPC | 4500129018 line item 026 | 2022-07-24 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV046 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20223 | Intel/Oregon/D1X | 5906010216 | 2021-12-26 | TPC | 4500129018 line item 027 | 2022-07-25 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV040 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20224 | Intel/Oregon/D1X | 5906010217 | 2021-12-27 | TPC | 4500129018 line item 028 | 2022-07-26 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV025 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20225 | Intel/Oregon/D1X | 5906010218 | 2021-12-28 | TPC | 4500129018 line item 029 | 2022-07-27 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV026 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20226 | Intel/Oregon/D1X | 5906010219 | 2021-12-29 | TPC | 4500129018 line item 030 | 2022-07-28 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV041 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20227 | Intel/Oregon/D1X | 5906010220 | 2021-12-30 | TPC | 4500129018 line item 031 | 2022-07-29 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-12-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Open
Q-20228 | Intel/Oregon/D1X | 5906010221 | 2021-12-31 | TPC | 4500129018 line item 032 | 2022-07-30 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2022-12-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Open
Q-20229 | Intel/Oregon/D1X | 5906010222 | 2022-01-01 | TPC | 4500129018 line item 033 | 2022-07-31 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2022-12-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Open
Q-20230 | Intel/Oregon/D1X | 5906010223 | 2022-01-02 | TPC | 4500129018 line item 034 | 2022-08-01 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2022-12-22 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Open
Q-20231 | Intel/Oregon/D1X | 5906010224 | 2022-01-03 | TPC | 4500129018 line item 035 | 2022-08-02 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20232 | Intel/Oregon/D1X | 5906010225 | 2022-01-04 | TPC | 4500129018 line item 036 | 2022-08-03 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20233 | Intel/Oregon/D1X | 5906010226 | 2022-01-05 | TPC | 4500129018 line item 037 | 2022-08-04 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV070 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20234 | Intel/Oregon/D1X | 5906010227 | 2022-01-06 | TPC | 4500129018 line item 038 | 2022-08-05 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV055 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20235 | Intel/Oregon/D1X | 5906010228 | 2022-01-07 | TPC | 4500129018 line item 039 | 2022-08-06 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20236 | Intel/Oregon/D1X | 5906010229 | 2022-01-08 | TPC | 4500129018 line item 040 | 2022-08-07 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20237 | Intel/Oregon/D1X | 5906010230 | 2022-01-09 | TPC | 4500129018 line item 041 | 2022-08-08 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20238 | Intel/Oregon/D1X | 5906010231 | 2022-01-10 | TPC | 4500129018 line item 042 | 2022-08-09 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02, 05 | 1 | 2022-08-30 |  | TPC |  |  | 777782139664 |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Closed
Q-20239 | Intel/Oregon/D1X | 5906010232 | 2022-01-11 | TPC | 4500129018 line item 043 | 2022-08-10 | 2311537 | 200455317 | 3 | EQ_ACDSys_LGD+B++_SNLE+++GC+++++F+_2++B | PN051 | [18 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-11-10 |  | TPC |  |  |  |  | Yes | https://mdigital.sharepoint.com/:b:/r/sites/Electronics/ElecEES/PolyFlow/6%20items%20of%20NCSR%20location%20for%20LG25%20PN051_20220711.pdf?csf=1&web=1 |  |  | Open
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | C-22944, PO Request Date: 1/18/2022 | [17 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV028 | 1 | 2022-08-30 | 70432 | TPC |  |  | 777782179039 |  | Yes |  |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV103 | 1 | 2022-08-30 | 70432 | TPC |  |  | 777782179039 |  | Yes |  |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV203 | 1 | 2022-08-30 | 70432 | TPC |  |  | 777782179039 |  | Yes |  |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV116 | 1 | 2022-08-30 | 70432 | TPC |  |  | 777782179039 |  | Yes |  |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV216 | 1 | 2022-08-30 | 70432 | TPC |  |  | 777782179039 |  | Yes |  |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV005 | 1 | 2022-08-30 | 70432 | TPC |  |  | 777782179039 |  | Yes |  |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV102 | 1 | 2022-08-30 | 70432 | TPC |  |  | 777782179039 |  | Yes |  |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV202 | 1 | 2022-08-30 | 70432 | TPC |  |  | 777782179039 |  | Yes |  |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2022-12-20 | 70432 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2022-12-20 | 70432 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | Flow controller | ENTEGRIS | 6500-T4-F04-D12-K-P7-U3 | FC122 | 1 | 2022-08-17 | 70432 | TPC |  |  | 777668074141 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | Flow controller | ENTEGRIS | 6500-T4-F04-D12-K-P7-U3 | FC222 | 1 | 2022-08-17 | 70432 | TPC |  |  | 777668074141 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | Flow controller | ENTEGRIS | 6500-T4-F04-D12-K-P7-U3 | FC123 | 1 | 2022-08-17 | 70432 | TPC |  |  | 777668074141 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-20259 | Intel/Arizona/F32 | 5906010831 LI 17 | 2022-01-04 | TPC | 4500129018 line item 020 | 2022-07-15 | 484959 | 200455318 | 4 | EQ_ACDSys_CBHDNJJPPDCC++++_BRD++++FLB+ | KOR122 | [18 empty] | Flow controller | ENTEGRIS | 6500-T4-F04-D12-K-P7-U3 | FC223 | 1 | 2022-08-17 | 70432 | TPC |  |  | 777668074141 |  | Yes | https://mdigital.sharepoint.com/sites/Electronics/ElecEES/PolyFlow/11%20items%20of%20NCSR%20location%20for%20LG%20JX051_20220509.pdf |  |  | Closed
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-07-14 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Received and installed before tool shipped
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV001 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV003 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV057 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV058 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV059 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV071 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV042 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV043 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV039 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV046 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV040 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV025 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV026 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV041 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV070 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV055 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2022-09-16 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-09-16 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02、NV05 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02、NV05 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-12-10 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-12-10 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T6-F04-D12-K-P7-U3 (1.1) | FC022 | 1 | 2022-12-10 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T6-F04-D12-K-P7-U3 (1.1) | FC026 | 1 | 2022-12-10 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC025 | 1 | 2022-08-03 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 070 | 2022-07-15 | 2309011 | 200453753 | 8 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UG621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021 | 1 | 2022-08-03 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-09-23 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Part received, installed befor tool shipped
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-07-22 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | SWAGELOK | NXT-DRP161AFJFJ-AWH | HV006 | 1 | 2022-07-14 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Part received, installed befor tool shipped
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV001 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV003 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV057 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV058 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV059 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV071 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV042 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV043 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV039 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV046 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV040 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV025 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV026 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV041 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV070 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV055 | 1 | 2022-08-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2022-09-16 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-09-16 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-12-10 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-07-14 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Part received, installed befor tool shipped
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 040 | 2022-07-22 | 2309011 | 200453750 | 5 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC029 |  | 2022-12-10 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV008 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV009 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV001 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV003 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV057 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV058 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV059 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV071 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV042 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV043 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV039 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV046 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV040 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV025 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV026 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV041 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV070 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | DS12-2C-12F-3 | CV055 | 1 | 2022-09-02 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2022-09-16 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 090 | 2022-07-28 | 2309011 | 200453761 | 10 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL621: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-09-16 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 5 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136767 | 2022-07-28 | 2313557 | 200458198 | 1 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL621: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 5 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136767 | 2022-07-28 | 2313557 | 200458198 | 1 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL621: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 5 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136767 | 2022-07-28 | 2313557 | 200458198 | 1 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL621: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 5 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136767 | 2022-07-28 | 2313557 | 200458198 | 1 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL621: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02、NV05 | 2 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 5 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136767 | 2022-07-28 | 2313557 | 200458198 | 1 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-12-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 5 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136767 | 2022-07-28 | 2313557 | 200458198 | 1 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-12-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2022-09-16 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-09-16 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 110 | 2022-08-01 | 2309011 | 200453763 | 12 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | WL611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-26 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-26 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-26 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02、NV05 | 2 | 2022-08-26 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-12-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-12-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC01 | 1 | 2022-08-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 3 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136770 | 2022-08-01 | 2313557 | 200458199 | 2 | EQ_ACDFK_LGD+B++_SMHE+++GC+D+++FS_2++B | WL611: Finishing Kit | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC02 | 1 | 2022-08-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV008 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV009 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-09-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2022-09-16 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 020 | 2022-08-05 | 2309011 | 200453748 | 3 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RR611: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-09-16 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136771 | 2022-08-05 | 2313328 | 200458200 | 2 | EQ_ACDFK_LGD+B++_AMMK+++GC+D+++F+_2++B | RR611: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-26 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136771 | 2022-08-05 | 2313328 | 200458200 | 2 | EQ_ACDFK_LGD+B++_AMMK+++GC+D+++F+_2++B | RR611: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02 | 1 | 2022-08-26 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136771 | 2022-08-05 | 2313328 | 200458200 | 2 | EQ_ACDFK_LGD+B++_AMMK+++GC+D+++F+_2++B | RR611: Finishing Kit | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21443 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136771 | 2022-08-05 | 2313328 | 200458200 | 2 | EQ_ACDFK_LGD+B++_AMMK+++GC+D+++F+_2++B | RR611: Finishing Kit | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC01 | 1 | 2022-08-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136771 | 2022-08-05 | 2313328 | 200458200 | 2 | EQ_ACDFK_LGD+B++_AMMK+++GC+D+++F+_2++B | RR611: Finishing Kit | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC02 | 1 | 2022-08-12 |  | TPC |  |  | Not Applicable |  | Yes |  |  |  | Closed | Factory Install
Q-21443 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136771 | 2022-08-05 | 2313328 | 200458200 | 2 | EQ_ACDFK_LGD+B++_AMMK+++GC+D+++F+_2++B | RR611: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC029 | 1 | 2022-11-21 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21443 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136771 | 2022-08-05 | 2313328 | 200458200 | 2 | EQ_ACDFK_LGD+B++_AMMK+++GC+D+++F+_2++B | RR611: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-11-21 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21443 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136771 | 2022-08-05 | 2313328 | 200458200 | 2 | EQ_ACDFK_LGD+B++_AMMK+++GC+D+++F+_2++B | RR611: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-11-21 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Circuit Breaker | EATON | ZEK35-UL | NA | 1 | 2022-09-06 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-11-04 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV064 | 1 | 2022-09-16 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-09-16 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV008 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV009 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 030 | 2022-08-12 | 2309011 | 200453749 | 4 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | RAK612: Slurry Base Build | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-09-12 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02、NV05 | 2 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV01 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV03 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV04 | 1 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | valves | ENTEGRIS | NVT4-T4-2 | NV02、NV05 | 2 | 2022-08-26 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T3-F04-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-11-30 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T3-F04-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-11-30 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC01 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC02 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 4 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136653 | 2022-08-12 | 2312625 | 200458201 | 2 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK612: Finishing Kit | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC01 | 1 | 2022-08-12 |  | TPC |  |  |  |  | Yes |  |  |  | Closed | Factory Installed
Q-21443 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136772 | 2022-08-19 | 2313330 | 200458202 | 1 | EQ_ACDFK_LGDSB++_SML++++GC+D+++F+_2++A | RE611: Finishing Kit | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 6 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136656 | 2022-08-19 | 2312625 | 200458203 | 3 | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | RAK623: Finishing Kit | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-10-14 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2022-10-21 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2022-10-21 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | Filter Housing bowl | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL021 | 1 | 2023-01-01 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | Filter Housing bowl | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL022 | 1 | 2023-01-01 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | Filter Housing bowl | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL101 | 1 | 2023-01-01 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | Filter Housing bowl | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL102 | 1 | 2023-01-01 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | Filter Housing bowl | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL201 | 1 | 2023-01-01 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | Filter Housing bowl | PALL FILTRATIONSTECHNIK GMB | FPT10-3/4FL-1/4FL | FL202 | 1 | 2023-01-01 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 2 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136658 | 2022-08-26 | 2312628 | 200458205 | 3 | EQ_ACDFK_HCCDNJ+++D++A+++_ARDSVBDFLBS+ | KF621: Finishing Kit | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 2 | 2022-10-31 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 | 2022-09-02 | 2309011 | 200453747 | 2 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | MV611: Slurry Base Build | [18 empty] | Scope Error | Scope Error | Scope Error | Scope Error | 1 | TBD |  | TPC |  |  |  |  | No |  |  |  | Open
Q-20403 | Intel/Ireland/F14 | 5906014284 | 2021-12-28 | TPC | 4500125151 | 2022-09-02 | 2309011 | 200453747 | 2 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | MV611: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC029 | 1 | 2022-11-21 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136657 | 2022-08-26 | 2312627 | 200458204 | 3 | EQ_ACDFK_HCCDNH+++D++B+++_BRDSVBDFLBM+ | HD622: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2022-12-09 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136657 | 2022-08-26 | 2312627 | 200458204 | 3 | EQ_ACDFK_HCCDNH+++D++B+++_BRDSVBDFLBM+ | HD622: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2022-12-09 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-05-31 | TPC | 4500136657 | 2022-08-26 | 2312627 | 200458204 | 3 | EQ_ACDFK_HCCDNH+++D++B+++_BRDSVBDFLBM+ | HD622: Finishing Kit | [18 empty] | Fitting | Fit-Line | UT8-12T-8N-3 | NA | 2 | 2022-11-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 050 | 2022-09-09 | 2309011 | 200453751 | 6 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UR621: Slurry Base Build | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-11-14 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 050 | 2022-09-09 | 2309011 | 200453751 | 6 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UR621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC025 | 1 | 2022-12-09 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 050 | 2022-09-09 | 2309011 | 200453751 | 6 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UR621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021 | 1 | 2022-12-09 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 050 | 2022-09-09 | 2309011 | 200453751 | 6 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UR621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-11-21 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20403 | Intel/Ireland/F24 | 5906014284 | 2021-12-28 | TPC | 4500125151 line item 050 | 2022-09-09 | 2309011 | 200453751 | 6 | EQ_ACDSys_LGD-B++_----+----+--++++_2++BE | UR621: Slurry Base Build | [18 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-11-21 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-12-08 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2022-12-08 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2022-12-08 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2022-12-08 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2022-12-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-21 |  | TPC |  |  | 770545115880 |  | Yes |  |  |  | Closed
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-12-08 |  | TPC |  |  | 770711110500 |  | Yes |  |  |  | Closed
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-12-08 |  | TPC |  |  | 770711110500 |  | Yes |  |  |  | Closed
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-12-08 |  | TPC |  |  | 770711110500 |  | Yes |  |  |  | Closed
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | 3 STA MANIFOLD ASSY | SMC | SS5Y31-03-DUX00330 | NA | 1 | 2022-12-08 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC01 | 1 | 2022-11-23 |  | TPC |  |  | 770559636400 |  | Yes |  |  |  | Closed
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC01 | 1 | 2022-11-23 |  | TPC |  |  | 770559636400 |  | Yes |  |  |  | Closed
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC02 | 1 | 2022-11-23 |  | TPC |  |  | 770559636400 |  | Yes |  |  |  | Closed
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-12-01 |  | TPC |  |  | 770611573649 |  | Yes |  |  |  | Closed
Q-21435 LI 3 | Intel/Arizona/F12 | 5906010831 LI 18 | 2022-06-16 | TPC | 4500143294 | 2022-09-23 | 2314126 | 200460297 | 2 | EQ_ACDSys_LGDSB++_SML++++GC+D+++F+_2++A | RE111 | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | LFU20-DUS01623 | FT030 | 1 | 2022-12-08 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 8 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140361 | 2022-09-09 | 2313327 | 200459464 | 1 | EQ_ACDFK_HCCDNHH++DC+B+++_BRDSVBDFLBM+ | JT621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2023-01-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 8 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140361 | 2022-09-09 | 2313327 | 200459464 | 1 | EQ_ACDFK_HCCDNHH++DC+B+++_BRDSVBDFLBM+ | JT621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2023-01-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 8 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140361 | 2022-09-09 | 2313327 | 200459464 | 1 | EQ_ACDFK_HCCDNHH++DC+B+++_BRDSVBDFLBM+ | JT621: Finishing Kit | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AE024/AT024 | 1 | 2022-11-14 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 8 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140361 | 2022-09-09 | 2313327 | 200459464 | 1 | EQ_ACDFK_HCCDNHH++DC+B+++_BRDSVBDFLBM+ | JT621: Finishing Kit | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 2 | 2022-11-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 8 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140361 | 2022-09-09 | 2313327 | 200459464 | 1 | EQ_ACDFK_HCCDNHH++DC+B+++_BRDSVBDFLBM+ | JT621: Finishing Kit | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 2 | 2022-11-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 7 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140144 | 2022-09-16 | 2313774 | 200459462 | 1 | EQ_ACDSys_HCCDNHA++D++B+++_BRDSVBDFLBS+ | HS621 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2023-01-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 7 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140144 | 2022-09-16 | 2313774 | 200459462 | 1 | EQ_ACDSys_HCCDNHA++D++B+++_BRDSVBDFLBS+ | HS621 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2023-01-05 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 7 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140144 | 2022-09-16 | 2313774 | 200459462 | 1 | EQ_ACDSys_HCCDNHA++D++B+++_BRDSVBDFLBS+ | HS621 | [18 empty] | Flow controller | ENTEGRIS | 6500-T0-F02-D12-K-P7-U3 | FC223 | 1 | 2023-04-30 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 7 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140144 | 2022-09-16 | 2313774 | 200459462 | 1 | EQ_ACDSys_HCCDNHA++D++B+++_BRDSVBDFLBS+ | HS621 | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 2 | 2022-11-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21442 LI 7 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140144 | 2022-09-16 | 2313774 | 200459462 | 1 | EQ_ACDSys_HCCDNHA++D++B+++_BRDSVBDFLBS+ | HS621 | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 2 | 2022-11-25 |  | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21144 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140365 | 2022-09-16 | 2314126 | 200459468 | 1 | EQ_ACDSYS_LGDSB++_SML++++GC+D+++F+_2++A | RE621 | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | LFU20-DUS01623 | FT030 | 1 | 2022-11-14 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21144 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140365 | 2022-09-16 | 2314126 | 200459468 | 1 | EQ_ACDSYS_LGDSB++_SML++++GC+D+++F+_2++A | RE621 | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | LFU20-DUS01623 | FT030 | 1 | 2022-11-14 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21144 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140365 | 2022-09-16 | 2314126 | 200459468 | 1 | EQ_ACDSYS_LGDSB++_SML++++GC+D+++F+_2++A | RE621 | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | 301070-0512 | LPC01 | 1 | 2022-10-15 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21144 LI 1 | Intel/Ireland/F24 | 5906014284 | 2022-06-21 | TPC | 4500140365 | 2022-09-16 | 2314126 | 200459468 | 1 | EQ_ACDSYS_LGDSB++_SML++++GC+D+++F+_2++A | RE621 | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-11-14 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20455 r3 LI 12 | Intel/Arizona/Eagle Mod 1 | 5906013402 | 2022-01-24 | TPC | 4500143303 | 2022-09-23 | 2310216 | 200460358 | 4 | EQ_ACDFK_HCCDNJ+++D++B+++_BRDSVBDFLBM+ | BT151: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2023-01-05 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20455 r3 LI 12 | Intel/Arizona/Eagle Mod 1 | 5906013402 | 2022-01-24 | TPC | 4500143303 | 2022-09-23 | 2310216 | 200460358 | 4 | EQ_ACDFK_HCCDNJ+++D++B+++_BRDSVBDFLBM+ | BT151: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2023-01-05 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20455 r3 LI 12 | Intel/Arizona/Eagle Mod 1 | 5906013402 | 2022-01-24 | TPC | 4500143303 | 2022-09-23 | 2310216 | 200460358 | 4 | EQ_ACDFK_HCCDNJ+++D++B+++_BRDSVBDFLBM+ | BT151: Finishing Kit | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 1 | 2022-11-25 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20455 r3 LI 12 | Intel/Arizona/Eagle Mod 1 | 5906013402 | 2022-01-24 | TPC | 4500143303 | 2022-09-23 | 2310216 | 200460358 | 4 | EQ_ACDFK_HCCDNJ+++D++B+++_BRDSVBDFLBM+ | BT151: Finishing Kit | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 1 | 2022-11-25 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20455 r3 LI 12 | Intel/Arizona/Eagle Mod 1 | 5906013402 | 2022-01-24 | TPC | 4500143303 | 2022-09-23 | 2310216 | 200460358 | 4 | EQ_ACDFK_HCCDNJ+++D++B+++_BRDSVBDFLBM+ | BT151: Finishing Kit | [18 empty] | fitting | Fit-Line | TFFR128N-3 | NA | 1 | 2023-05-25 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-20455 r3 LI 12 | Intel/Arizona/Eagle Mod 1 | 5906013402 | 2022-01-24 | TPC | 4500143303 | 2022-09-23 | 2310216 | 200460358 | 4 | EQ_ACDFK_HCCDNJ+++D++B+++_BRDSVBDFLBM+ | BT151: Finishing Kit | [18 empty] | fitting | Fit-Line | TFFR128N-3 | NA | 1 | 2023-05-25 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21381 LI 1 | Intel/Oregon/ | 5906010199 | 2022-06-09 | TPC | 4500145037 | 2022-10-14 | 2313195 | 200460943 | 1 | EQ_ACDSys_HCCDNL+++DC+B+++_BRDSVBDFLBM+ | SW041 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2023-01-05 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21381 LI 1 | Intel/Oregon/ | 5906010199 | 2022-06-09 | TPC | 4500145037 | 2022-10-14 | 2313195 | 200460943 | 1 | EQ_ACDSys_HCCDNL+++DC+B+++_BRDSVBDFLBM+ | SW041 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2023-01-05 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21381 LI 1 | Intel/Oregon/ | 5906010199 | 2022-06-09 | TPC | 4500145037 | 2022-10-14 | 2313195 | 200460943 | 1 | EQ_ACDSys_HCCDNL+++DC+B+++_BRDSVBDFLBM+ | SW041 | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AE024/AT024 | 1 | 2022-12-01 | 44879 | TPC |  |  | 770611525842 |  | Yes |  |  |  | Open
Q-21381 LI 1 | Intel/Oregon/ | 5906010199 | 2022-06-09 | TPC | 4500145037 | 2022-10-14 | 2313195 | 200460943 | 1 | EQ_ACDSys_HCCDNL+++DC+B+++_BRDSVBDFLBM+ | SW041 | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 1 | 2022-12-09 | 44879 | TPC |  |  | 770725018868 |  | Yes |  |  |  | Closed
Q-21381 LI 1 | Intel/Oregon/ | 5906010199 | 2022-06-09 | TPC | 4500145037 | 2022-10-14 | 2313195 | 200460943 | 1 | EQ_ACDSys_HCCDNL+++DC+B+++_BRDSVBDFLBM+ | SW041 | [18 empty] | fitting | Fit-Line | UT8-12T-8N-3 | NA | 1 | 2022-12-09 | 44879 | TPC |  |  | 770725018868 |  | Yes |  |  |  | Closed
Q-21381 LI 1 | Intel/Oregon/ | 5906010199 | 2022-06-09 | TPC | 4500145037 | 2022-10-14 | 2313195 | 200460943 | 1 | EQ_ACDSys_HCCDNL+++DC+B+++_BRDSVBDFLBM+ | SW041 | [18 empty] | fitting | Fit-Line | TFFR128N-3 | NA | 1 | 2023-05-25 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21381 LI 1 | Intel/Oregon/ | 5906010199 | 2022-06-09 | TPC | 4500145037 | 2022-10-14 | 2313195 | 200460943 | 1 | EQ_ACDSys_HCCDNL+++DC+B+++_BRDSVBDFLBM+ | SW041 | [18 empty] | fitting | Fit-Line | TFFR128N-3 | NA | 1 | 2023-05-25 | 44879 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21625 LI 1 | Intel/Ireland/F24 | 5905014284 | 2022-06-21 | TPC | 4500140362 | 2022-09-02 | 2314128 | 200459465 | 1 | EQ_ACDFK_LGD+B++_ANLA+++GC+++++F+_2++B | UA621: Finishing Kit | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | TBD | 80452 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21625 LI 1 | Intel/Ireland/F24 | 5905014284 | 2022-06-21 | TPC | 4500140362 | 2022-09-02 | 2314128 | 200459465 | 1 | EQ_ACDFK_LGD+B++_ANLA+++GC+++++F+_2++B | UA621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC029 | 1 | 2022-10-12 | 80452 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21625 LI 1 | Intel/Ireland/F24 | 5905014284 | 2022-06-21 | TPC | 4500140362 | 2022-09-02 | 2314128 | 200459465 | 1 | EQ_ACDFK_LGD+B++_ANLA+++GC+++++F+_2++B | UA621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC025 | 1 | TBD | 80452 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21625 LI 1 | Intel/Ireland/F24 | 5905014284 | 2022-06-21 | TPC | 4500140362 | 2022-09-02 | 2314128 | 200459465 | 1 | EQ_ACDFK_LGD+B++_ANLA+++GC+++++F+_2++B | UA621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC021 | 1 | TBD | 80452 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21625 LI 1 | Intel/Ireland/F24 | 5905014284 | 2022-06-21 | TPC | 4500140362 | 2022-09-02 | 2314128 | 200459465 | 1 | EQ_ACDFK_LGD+B++_ANLA+++GC+++++F+_2++B | UA621: Finishing Kit | [18 empty] | Flow controller | ENTEGRIS | 6500-T0-F02-D12-K-P7-U3 | FC027 | 1 | 2023-04-30 | 80452 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | SOL1 | 1 | 2022-11-25 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-25 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-25 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-25 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-25 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | 3 STA MANIFOLD ASSY | SMC | SS5Y31-06-DUX00035 | SOL2 | 1 | 2022-11-10 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2023-03-08 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2023-03-08 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2023-03-08 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2023-03-08 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2023-03-08 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-03-DUX00330 | NA | 1 | 2022-11-10 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-12-28 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Flow controller | ENTEGRIS | 6500-T1-F03-D12-K-P7-U3 (1.1) | FC029 | 1 | 2022-12-05 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC023 | 1 | 2022-12-30 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 2 | Intel/Arizona/F12 | 5906010831 LI 20 | 2022-08-10 | TPC | 4500144560 | 2022-10-21 | 2314374 | 200460941 | 1 | EQ_ACDSys_LGD+B++_AMMK+++GC+D+++F+_2++B | RR111 | [18 empty] | Flow controller | ENTEGRIS | 6500-T5-F04-D12-K-P7-U3 (1.1) | FC027 | 1 | 2022-12-30 | 80570 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | SOL1 | 1 | 2022-11-18 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-18 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-18 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-18 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-12-DUX00013 | NA | 1 | 2022-11-18 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | 3 STA MANIFOLD ASSY | SMC | SS5Y31-06-DUX00035 | SOL2 | 1 | 2022-11-10 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2023-03-08 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL02 | 1 | 2023-03-08 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL03 | 1 | 2023-03-08 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL04 | 1 | 2023-03-08 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Filter Housing bowl | ENTEGRIS | YY66B2280 | FL01 | 1 | 2023-03-08 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV008 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV009 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV027 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV028 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV029 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV030 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV031 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV032 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV037 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV038 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | valves | ENTEGRIS | 202-71-01-3 | CV051 | 1 | 2022-12-01 | 80571 | TPC |  |  | 770626806951 |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | 12 STA MANIFOLD ASSY | SMC | SS5Y31-03-DUX00330 | NA | 1 | 2022-11-12 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-12-18 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | LPC sensor | PARTICLE MEASURING SYSTEM | LFU20-DUS01623 | FT030 | 1 | 2022-12-16 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC023 | 1 | 2023-01-30 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Flow controller | ENTEGRIS | 6500-T2-F03-D12-K-P7-U3 (1.1) | FC027 | 1 | 2023-01-30 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 4 | Intel/Arizona/F12 | 5906010831 LI 21 | 2022-08-10 | TPC | 4500145032 | 2022-10-28 | 2314375 | 200460942 | 1 | EQ_ACDSys_LGD+B++_SMHE+++GC+D+++FS_2++B | WL111 | [18 empty] | Flow controller | ENTEGRIS | 6500-T3-F04-D12-K-P7-U3 (1.1) | FC026 | 1 | 2022-12-24 | 80571 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 1 | Intel/Arizona/F12 | 5906010831 LI 19 | 2022-06-16 | TPC | 4500143295 | 2022-11-04 | 484959 | 200460298 | 5 | EQ_ACDSYS_CBHDNJJ++DCC++++_BRD++++FLBM+ | KOR111 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2022-11-19 | 80659 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 1 | Intel/Arizona/F12 | 5906010831 LI 19 | 2022-06-16 | TPC | 4500143295 | 2022-11-04 | 484959 | 200460298 | 5 | EQ_ACDSYS_CBHDNJJ++DCC++++_BRD++++FLBM+ | KOR111 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2022-11-19 | 80659 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21435 LI 1 | Intel/Arizona/F12 | 5906010831 LI 19 | 2022-06-16 | TPC | 4500143295 | 2022-11-04 | 484959 | 200460298 | 5 | EQ_ACDSYS_CBHDNJJ++DCC++++_BRD++++FLBM+ | KOR111 | [18 empty] | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AE024/AT024 | 1 | 2022-11-19 | 80659 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21523 | Intel/Arizona/F12 | 5906010831 LI 22 | 2022-08-10 | TPC | 4500143296 | 2022-12-02 | 2314342 | 200460299 | 1 | EQ_ACDSys_CBHDNHA++D++B+++_BRDHVBDFLAM+ | HS142 | [18 empty] | fitting | Fit-Line | UE812TN-3 | NA | 1 | TBD | 80876 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21523 | Intel/Arizona/F12 | 5906010831 LI 22 | 2022-08-10 | TPC | 4500143296 | 2022-12-02 | 2314342 | 200460299 | 1 | EQ_ACDSys_CBHDNHA++D++B+++_BRDHVBDFLAM+ | HS142 | [18 empty] | fitting | Fit-Line | UE812TN-3 | NA | 1 | TBD | 80876 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21523 | Intel/Arizona/F12 | 5906010831 LI 22 | 2022-08-10 | TPC | 4500143296 | 2022-12-02 | 2314342 | 200460299 | 1 | EQ_ACDSys_CBHDNHA++D++B+++_BRDHVBDFLAM+ | HS142 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2023-01-05 | 80876 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21523 | Intel/Arizona/F12 | 5906010831 LI 22 | 2022-08-10 | TPC | 4500143296 | 2022-12-02 | 2314342 | 200460299 | 1 | EQ_ACDSys_CBHDNHA++D++B+++_BRDHVBDFLAM+ | HS142 | [18 empty] | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2023-01-05 | 80876 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21523 | Intel/Arizona/F12 | 5906010831 LI 22 | 2022-08-10 | TPC | 4500143296 | 2022-12-02 | 2314342 | 200460299 | 1 | EQ_ACDSys_CBHDNHA++D++B+++_BRDHVBDFLAM+ | HS142 | [18 empty] | Flow controller | ENTEGRIS | 6500-T3-F04-D12-K-P7-U3 (1.1) | FC122 | 1 | 2023-02-24 | 80876 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21523 | Intel/Arizona/F12 | 5906010831 LI 22 | 2022-08-10 | TPC | 4500143296 | 2022-12-02 | 2314342 | 200460299 | 1 | EQ_ACDSys_CBHDNHA++D++B+++_BRDHVBDFLAM+ | HS142 | [18 empty] | Flow controller | ENTEGRIS | 6500-T3-F04-D12-K-P7-U3 (1.1) | FC222 | 1 | 2023-02-24 | 80876 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21523 | Intel/Arizona/F12 | 5906010831 LI 22 | 2022-08-10 | TPC | 4500143296 | 2022-12-02 | 2314342 | 200460299 | 1 | EQ_ACDSys_CBHDNHA++D++B+++_BRDHVBDFLAM+ | HS142 | [18 empty] | Flow controller | ENTEGRIS | 6500-T0-F02-D12-K-P7-U3 | FC223 | 1 | 2023-04-30 | 80876 | TPC |  |  |  |  | Yes |  |  |  | Open
Q-21523 | Intel/Arizona/F12 | 5906010831 LI 22 | 2022-08-10 | TPC | 4500143296 | 2022-12-02 | 2314342 | 200460299 | 1 | EQ_ACDSys_CBHDNHA++D++B+++_BRDHVBDFLAM+ | HS142 | [18 empty] | Fitting | Fit-Line | UT8-12T-8N-3 | NA | 1 | 2022-12-24 | 80876 | TPC |  |  |  |  | Yes |  |  |  | Open
Note on L34: Bernard Klees: Changed from KF122 10/8/21
Note on L36: Bernard Klees: Changed from KF122 10/8/21

## Sheet2
Item no | Tools Ship Date | Tool Code | 40 character | Component Type | Vendor | NCSR parts number | Tag Number | QTY | Parts estimated ship date
599 | 2022-09-16 | RAK623(2309011) | EQ_ACDUB_LGD-B++_----+----+--++++_2++BE | valves | ENTEGRIS | 201-46-01-3 | HV065 | 1 | 2022-11-15
600 | 2022-09-16 | RAK623(2312625) | EQ_ACDFK_LGDSB++_SMMH+++GC+++++FS_2++B | Analysis | ENTEGRIS | CPAAALAXX4F4F (KIT 1 CR288) | AT025/AE025 | 1 | 2022-10-20
609 | 2022-09-16 | HD622(2312627) | EQ_ACDFK_HCCDNH+++D++B+++_BRDSVBDFLBM+ | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC121 | 1 | 2022-10-25
610 | 2022-09-16 | HD622(2312627) | EQ_ACDFK_HCCDNH+++D++B+++_BRDSVBDFLBM+ | Flow controller | ENTEGRIS | 6501-T8-F06-D12-K-P7-U3-M36 | FC221 | 1 | 2022-10-25
622 | 2022-09-16 | HD622(2312627) | EQ_ACDFK_HCCDNH+++D++B+++_BRDSVBDFLBM+ | fitting | Fit-Line | UT8-12T-8N-3 | NA | 2 | 2022-11-25

## Pivot Table
Open Closed | Open
Count of Part Quantity
Tool ID# | Component | Discrepant Part Number | Discrepant Part Mfg. | Part Est Ship Date | Total
CD051 | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6
| Filter Housing | YY6620A2FE | ENTEGRIS | 2022-11-04 | 5
| Flow controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-26 | 2
CD051 Total |  |  |  |  | 13
EW051 | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 1
| Flow Controller | 6500-T3-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-10-17 | 2
EW051 Total |  |  |  |  | 3
GN051 | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5
| Flow controller | 6500-T3-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-10-17 | 2
GN051 Total |  |  |  |  | 7
JV051 | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-11-04 | 5
JV051 Total |  |  |  |  | 5
JX051 | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 4
|  |  |  | 2022-10-04 | 1
| Flow controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-26 | 2
| USB Cable | 4CM310 | LIMNDY | NA | 1
JX051 Total |  |  |  |  | 8
PCU802 | Valves | 203-1414-215 | ENTEGRIS | 2022-05-05 | 1
PCU802 Total |  |  |  |  | 1
PN051 | Filter Housing bowl | YY66B2280 | ENTEGRIS | 2022-12-22 | 5
| Flow controller | 6500-T2-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-11-10 | 1
PN051 Total |  |  |  |  | 6
RV041 | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 2
RV041 Total |  |  |  |  | 2
VC121D | Flow Controller | 6500-T1-F02-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-17 | 1
VC121D Total |  |  |  |  | 1
KOR122 | Flow controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2022-12-20 | 2
KOR122 Total |  |  |  |  | 2
UG621: Slurry Base Build | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6
| Filter Housing bowl | YY66B2280 | ENTEGRIS | 2022-11-04 | 5
| Flow Controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2022-08-03 | 2
| Flow controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-10 | 2
|  | 6500-T6-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-10 | 2
| Valves | 201-46-01-3 | ENTEGRIS | 2022-09-16 | 2
|  | DS12-2C-12F-3 | ENTEGRIS | 2022-08-05 | 16
|  | NVT4-T4-2 | ENTEGRIS | 2022-08-26 | 8
UG621: Slurry Base Build Total |  |  |  |  | 43
RR621: Slurry Base Build | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6
| Filter Housing bowl | YY66B2280 | ENTEGRIS | 2022-11-04 | 5
| Flow Controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-10
| Flow controller | 6500-T5-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-10 | 1
| Valves | 201-46-01-3 | ENTEGRIS | 2022-09-16 | 2
|  | 202-71-01-3 | ENTEGRIS | 2022-08-12 | 9
|  | DS12-2C-12F-3 | ENTEGRIS | 2022-08-05 | 16
|  | NVT4-T4-2 | ENTEGRIS | 2022-08-26 | 2
RR621: Slurry Base Build Total |  |  |  |  | 41
WL621: Slurry Base Build | Circuit Breaker | ZEK35-UL | EATON | 2022-09-06 | 6
| Filter Housing bowl | YY66B2280 | ENTEGRIS | 2022-11-04 | 5
| Valves | 201-46-01-3 | ENTEGRIS | 2022-09-16 | 2
|  | 202-71-01-3 | ENTEGRIS | 2022-09-12 | 11
|  | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 16
WL621: Slurry Base Build Total |  |  |  |  | 40
WL621: Finishing Kit | Flow Controller | 6500-T2-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-25 | 1
| Flow controller | 6500-T2-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-25 | 1
| Valves | NVT4-T4-2 | ENTEGRIS | 2022-08-26 | 4
WL621: Finishing Kit Total |  |  |  |  | 6
WL611: Finishing Kit | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-10-14 | 1
| Flow Controller | 6500-T2-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-25 | 2
WL611: Finishing Kit Total |  |  |  |  | 3
RR611: Finishing Kit | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-10-14 | 1
| Flow Controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-11-21 | 1
| Flow controller | 6500-T5-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-11-21 | 2
RR611: Finishing Kit Total |  |  |  |  | 4
RAK612: Slurry Base Build | Circuit Breaker | ZEK35-UL | EATON | 2022-09-06 | 6
| Filter Housing bowl | YY66B2280 | ENTEGRIS | 2022-11-04 | 5
| Valves | 201-46-01-3 | ENTEGRIS | 2022-09-16 | 2
|  | 202-71-01-3 | ENTEGRIS | 2022-09-12 | 11
RAK612: Slurry Base Build Total |  |  |  |  | 24
RAK612: Finishing Kit | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-10-14 | 1
RAK612: Finishing Kit Total |  |  |  |  | 1
RE611: Finishing Kit | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-10-14 | 1
RE611: Finishing Kit Total |  |  |  |  | 1
RAK623: Finishing Kit | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-10-14 | 1
RAK623: Finishing Kit Total |  |  |  |  | 1
KF621: Finishing Kit | Filter Housing bowl | FPT10-3/4FL-1/4FL | PALL FILTRATIONSTECHNIK GMB | 2023-01-01 | 6
| Fitting | UT8-12T-8N-3 | Fit-Line | 2022-10-31 | 1
| Flow controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2022-10-21 | 2
KF621: Finishing Kit Total |  |  |  |  | 9
MV611: Slurry Base Build | Flow Controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-11-21 | 1
| Scope Error | Scope Error | Scope Error | TBD | 1
MV611: Slurry Base Build Total |  |  |  |  | 2
HD622: Finishing Kit | Fitting | UT8-12T-8N-3 | Fit-Line | 2022-11-25 | 1
| Flow controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2022-12-09 | 2
HD622: Finishing Kit Total |  |  |  |  | 3
UR621: Slurry Base Build | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-11-14 | 1
| Flow Controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2022-12-09 | 2
| Flow controller | 6500-T5-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-11-21 | 2
UR621: Slurry Base Build Total |  |  |  |  | 5
RE111 | Filter Housing bowl | YY66B2280 | ENTEGRIS | 2022-12-08 | 4
|  |  |  | 2022-12-05 | 1
| LPC Sensor | LFU20-DUS01623 | PARTICLE MEASURING SYSTEM | 2022-12-08 | 1
| 3 STA MANIFOLD ASSY | SS5Y31-03-DUX00330 | SMC | 2022-12-08 | 1
RE111 Total |  |  |  |  | 7
JT621: Finishing Kit | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-11-14 | 1
| Fitting | UT8-12T-8N-3 | Fit-Line | 2022-11-25 | 2
| Flow controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2023-01-05 | 2
JT621: Finishing Kit Total |  |  |  |  | 5
HS621 | Fitting | UT8-12T-8N-3 | Fit-Line | 2022-11-25 | 2
| Flow controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2023-01-05 | 2
|  | 6500-T0-F02-D12-K-P7-U3 | ENTEGRIS | 2023-04-30 | 1
HS621 Total |  |  |  |  | 5
RE621 | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-11-14 | 1
| LPC Sensor | 301070-0512 | PARTICLE MEASURING SYSTEM | 2022-10-15 | 1
|  | LFU20-DUS01623 | PARTICLE MEASURING SYSTEM | 2022-11-14 | 2
RE621 Total |  |  |  |  | 4
BT151: Finishing Kit | Fitting | UT8-12T-8N-3 | Fit-Line | 2022-11-25 | 2
|  | TFFR128N-3 | Fit-Line | 2023-05-25 | 2
| Flow controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2023-01-05 | 2
BT151: Finishing Kit Total |  |  |  |  | 6
SW041 | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-12-01 | 1
| Fitting | TFFR128N-3 | Fit-Line | 2023-05-25 | 2
| Flow controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2023-01-05 | 2
SW041 Total |  |  |  |  | 5
UA621: Finishing Kit | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | TBD | 1
| Flow Controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-10-12 | 1
|  | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | TBD | 2
|  | 6500-T0-F02-D12-K-P7-U3 | ENTEGRIS | 2023-04-30 | 1
UA621: Finishing Kit Total |  |  |  |  | 5
RR111 | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-12-28 | 1
| Filter Housing bowl | YY66B2280 | ENTEGRIS | 2023-03-08 | 5
| Flow Controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-05 | 1
| Flow controller | 6500-T5-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-30 | 2
| 12 STA MANIFOLD ASSY | SS5Y31-12-DUX00013 | SMC | 2022-11-25 | 5
|  | SS5Y31-03-DUX00330 | SMC | 2022-11-10 | 1
| 3 STA MANIFOLD ASSY | SS5Y31-06-DUX00035 | SMC | 2022-11-10 | 1
RR111 Total |  |  |  |  | 16
WL111 | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-12-18 | 1
| Filter Housing bowl | YY66B2280 | ENTEGRIS | 2023-03-08 | 5
| Flow Controller | 6500-T2-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2023-01-30 | 2
|  | 6500-T3-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-12-24 | 1
| LPC Sensor | LFU20-DUS01623 | PARTICLE MEASURING SYSTEM | 2022-12-16 | 1
| Valves | 202-71-01-3 | ENTEGRIS | 2022-12-01 | 11
| 12 STA MANIFOLD ASSY | SS5Y31-12-DUX00013 | SMC | 2022-11-18 | 5
|  | SS5Y31-03-DUX00330 | SMC | 2022-11-12 | 1
| 3 STA MANIFOLD ASSY | SS5Y31-06-DUX00035 | SMC | 2022-11-10 | 1
WL111 Total |  |  |  |  | 28
KOR111 | Analysis | CPAAALAXX4F4F (KIT 1 CR288) | ENTEGRIS | 2022-11-19 | 1
| Flow controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2022-11-19 | 2
KOR111 Total |  |  |  |  | 3
HS142 | Fitting | UT8-12T-8N-3 | Fit-Line | 2022-12-24 | 1
|  | UE812TN-3 | Fit-Line | TBD | 2
| Flow Controller | 6501-T8-F06-D12-K-P7-U3-M36 | ENTEGRIS | 2023-01-05 | 2
|  | 6500-T3-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2023-02-24 | 2
|  | 6500-T0-F02-D12-K-P7-U3 | ENTEGRIS | 2023-04-30 | 1
HS142 Total |  |  |  |  | 8
Grand Total |  |  |  |  | 323

## Ship To Information
Customer/Location | Supplier | Finish Date | MM# | Equipment # | Serial # | Tool ID# | Ship To: | Address | Phone # | Comments
Intel/Oregon/D1X-Mod3 | TPC | 2022-06-22 | 2311537 | 200449600 | 2 | JV051 | Aaron Balliett | Intel 2501 NE Century Blvd Hillsboro, OR 97124 Attn: PCD, Fab D1X | +1 (512) 672-3686 | Transition date 6/15/22 Brian to Aaron
Intel/Oregon/D1X-Mod3 | TPC | 2022-06-22 | 2311535 | 200449595 | 1 | CD051 | Aaron Balliett | Intel 2501 NE Century Blvd Hillsboro, OR 97124 Attn: PCD, Fab D1X | +1 (512) 672-3686 | Transition date 6/15/22 Brian to Aaron
Intel/Ireland/F24 | TPC | 2022-07-08 | 483336 | 200449601 | 1 | SNK711 | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Oregon/D1X | TPC | 2022-07-08 | 2311537 | 200455317 | 3 | PN051 | Aaron Balliett | Intel 2501 NE Century Blvd Hillsboro, OR 97124 Attn: PCD, Fab D1X | +1 (512) 672-3686 | Transition date 6/15/22 Brian to Aaron
Intel/Arizona/F32 | TPC | 2022-07-15 | 484959 | 200455318 | 4 | KOR122 | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85303 | +1 (602) 228-2343
Intel/Ireland/F24 | TPC | 2022-07-15 | 2313775 | 200458196 | 1 | UG621: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-07-15 | 2309011 | 200453753 | 8 | UG621: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-07-22 | 487982 | 200453933 | 22 | PCU303 | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-07-22 | 2313328 | 200458197 | 1 | RR621: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-07-22 | 2309011 | 200453750 | 5 | RR621: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-05 | 2313557 | 200458198 | 1 | WL621: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-05 | TBD | TBD | TBD | AA031: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-05 | 2309011 | 200453760 | 9 | AA031: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-05 | 2309011 | 200453761 | 10 | WL621: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F14 | TPC | 2022-08-12 | 2309011 | 200453747 | 2 | MV011: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-12 | TBD | TBD | TBD | MV011: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-12 | 2313557 | TBD | TBD | WL611: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-12 | 2309011 | 200453763 | 12 | WL611: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F14 | TPC | 2022-08-19 | 2309011 | 200453748 | 3 | RR611: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F14 | TPC | 2022-08-19 | 2309011 | 200453749 | 4 | RAK612: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-19 | 2313328 | TBD | TBD | RR611: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-19 | 2312625 | TBD | TBD | RAK612: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-26 | 2313330 | TBD | TBD | RE611: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-26 | TBD | TBD | TBD | UR621 or UA621: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-26 | 2309011 | 200453751 | 6 | UA621: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-08-26 | 2309011 | 200453752 | 7 | RE611: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-09-02 | 2312625 | TBD | TBD | RAK623: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-09-02 | 2313327 | TBD | TBD | JT611: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-09-02 | 2309019 | 200453754 | 5 | JT611: HCCB Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-09-02 | 2309011 | 200453762 | 11 | RAK623: Slurry Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-09-09 | 2312627 | TBD | TBD | HD622: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-09-09 | 2312628 | TBD | TBD | KF621: Finishing Kit | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-09-09 | 2309019 | 200453755 | 6 | HD622: HCCB Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Ireland/F24 | TPC | 2022-09-09 | 2309019 | 200453756 | 7 | KF621: HCCB Base Build | Liam Kelly | Merck - Versum Materials, Intel Ireland Collinstown Industrial Estate, IR4 building, 1st floor Desk location 402 Leixlip, Co Kildare Ireland | +353-87-664-3817
Intel/Arizona/Eagle Mod 1 | TPC | 2022-09-16 | 2309019 | 200455777 | 19 | KOR151: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-09-16 | 2309019 | TBD | TBD | KOR152: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-09-23 | 2309019 | TBD | TBD | BT151: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-10-07 | 2309019 | TBD | TBD | BH151: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-10-07 | 2309019 | TBD | TBD | BT152: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-10-14 | 2309011 | 200455771 | 24 | TM151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-10-14 | 2309011 | 200455772 | 25 | RFT151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/New Mexico/F11X | TPC | 2022-10-17 | 487982 | 200457424 | 29 | TEV636 | Lance Bennitt | Intel, 1600 RIO RANCHO BLVD S E, RIO RANCHO, NM 87124 | +1 (505) 893-6383 | lance.t.bennett@intel.com
Intel/Arizona/Eagle Mod 1 | TPC | 2022-10-21 | 2309011 | 200455773 | 26 | JS151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-10-21 | 2309019 | TBD | TBD | SSC151: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-10-28 | 2309011 | 200455774 | 27 | RZ151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-10-28 | 2309019 | TBD | TBD | KG151: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-11-04 | 2309011 | 200455775 | 28 | VC151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-11-04 | 2309011 | 200455776 | 29 | FB151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-12-02 | 2309019 | TBD | TBD | HD151: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-12-02 | 2309019 | TBD | TBD | KF151: HCCB Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-12-09 | 2309011 | 200455778 | 30 | CH151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-12-09 | 2309011 | TBD | TBD | DSS151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/New Mexico/F11X | TPC | 2022-12-09 | 488159 | 200454028 | 10 | AFW846 | Tafoya, Gabriella | Intel, 1600 RIO RANCHO BLVD S E, RIO RANCHO, NM 87124 | TBD | gabriella.tafoya@intel.com
Intel/Arizona/Eagle Mod 1 | TPC | 2022-12-16 | 2309011 | TBD | TBD | KB151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/Arizona/Eagle Mod 1 | TPC | 2022-12-16 | 2309011 | TBD | TBD | RAK151: Slurry Base Build | Robin Davis | EMD Electronics 8555 South River Parkway Tempe, AZ 85284 | +1 (602) 228-2343
Intel/New Mexico/F11X | TPC | 2022-12-16 | 488159 | 200454029 | 11 | AFW847 | Tafoya, Gabriella | Intel, 1600 RIO RANCHO BLVD S E, RIO RANCHO, NM 87124 | TBD | gabriella.tafoya@intel.com
Intel/New Mexico/F11X | TPC | 2022-12-19 | 487982 | 200457425 | 30 | TEV637 | Lance Bennitt | Intel, 1600 RIO RANCHO BLVD S E, RIO RANCHO, NM 87124 | +1 (505) 893-6383 | lance.t.bennett@intel.com
Intel/New Mexico/F11X | TPC | 2022-12-23 | 488159 | 200454030 | 12 | AFW848 | Tafoya, Gabriella | Intel, 1600 RIO RANCHO BLVD S E, RIO RANCHO, NM 87124 | TBD | gabriella.tafoya@intel.com

## Compare 062222
Open Closed | Open |  |  |  |  | Close/ Open | Open
|  | EMD TRACKER | [5 empty] | TPC TRACKER
Count of Part Quantity | [5 empty] | Sum of QTY
Tool ID# | Component | Discrepant Part Number | Discrepant Part Mfg. | Part Est Ship Date | Total | Tool Code | Component Type | NCSR parts number | Vendor | Parts estimated ship date | Total | Comments
CD051 | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6 | CD051 (2311535) | Circuit Breaker | ZEK35-UL | Eaton | 2022-07-22 | 6
| Filter Housing | YY6620A2FE | ENTEGRIS | 2022-11-04 | 5 |  | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-11-04 | 5
| Flow controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-26 | 2 |  | Flow controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-26 | 2
| Valves | 201-46-01-3 | ENTEGRIS | 2022-09-16 | 2 |  | valves | 201-46-01-3 | ENTEGRIS | 2022-09-16 | 2
|  | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 16 |  |  | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 16
|  | NVT4-T4-2 | ENTEGRIS | 2022-08-25 | 5 |  |  | NVT4-T4-2 | ENTEGRIS | 2022-08-25 | 4
CD051 Total |  |  |  |  | 36 | CD051 (2311535) Total |  |  |  |  | 35
EW051 | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6 | EW051D(2311536) | Circuit Breaker | ZEK35-UL | Eaton | 2022-07-22 | 6
| Filter | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5 |  | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5
| Flow Controller | 6500-T3-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-10-17 | 2 |  | Flow controller | 6500-T3-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-10-17 | 2
EW051 Total |  |  |  |  | 13 | EW051D(2311536) Total |  |  |  |  | 13
GN051 | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6 | GN051(2311536) | Circuit Breaker | ZEK35-UL | Eaton | 2022-07-22 | 6
| Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5 |  | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5
| Flow controller | 6500-T3-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-10-17 | 2 |  | Flow controller | 6500-T3-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-10-17 | 2
|  | 6500-T5-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-06-30 | 2 |  |  | 6500-T5-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-06-30 | 2
| Valves | NVT4-T4-2 | ENTEGRIS | 2022-08-18 | 5 |  | valves | NVT4-T4-2 | ENTEGRIS | 2022-08-18 | 4 | NV02, NV05?
GN051 Total |  |  |  |  | 20 | GN051(2311536) Total |  |  |  |  | 19
JV051 | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6 | JV051 (2311537) | Circuit Breaker | ZEK35-UL | Eaton | 2022-07-22 | 6
| Filter Housing | YY6620A2FE | ENTEGRIS | 2022-11-04 | 5 |  | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-11-04 | 5
| Valves | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 16 |  | valves | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 16
|  | NVT4-T4-2 | ENTEGRIS | 2022-08-25 | 5 |  |  | NVT4-T4-2 | ENTEGRIS | 2022-08-18 | 4 | NV02, NV05?
JV051 Total |  |  |  |  | 32 | JV051 (2311537) Total |  |  |  |  | 31
JX051 | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6 | JX051(2311534) | Circuit Breaker | ZEK35-UL | Eaton | 2022-07-22 | 6
| Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5 |  | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5
| Flow controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-26 | 2 |  | Flow controller | 6500-T1-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-26 | 2
|  | 6500-T4-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-22 | 2 |  |  | 6500-T4-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-22 | 2
| USB Cable | 4CM310 | LIMNDY | NA | 1 |  | USB CABLE | (blank) | LINDY | NA | 1
| Valves | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 15 |  | valves | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 15
|  | NVT4-T4-2 | ENTEGRIS | 2022-08-18 | 5 |  |  | NVT4-T4-2 | ENTEGRIS | 2022-08-18 | 4 | NV02, NV05?
JX051 Total |  |  |  |  | 36 | JX051(2311534) Total |  |  |  |  | 35
KF122 | Filter | FPT10-3/4FL-1/4FL | PALL FILTRATIONSTECHNIK GMB | 2022-07-08 | 6 | KF122 (2305744) | Filter | FPT10-3/4FL-1/4FL | PALL FILTRATIONSTECHNIK GMB | 2022-07-08 | 6
[7 empty] | valves | 202-71-01-3 | ENTEGRIS | 2022-07-08 | 14 | Qty (14) shipped 6/22
| Valves | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 11 |  | valves | DS12-2C-12F-3 | ENTEGRIS | 2022-09-02 | 11
| Vessel Pressure | 153-601-156 | ENTEGRIS | 2022-08-29 | 4 |  | Vessel Pressure | 153-601-156 | ENTEGRIS | 2022-08-29 | 4
KF122 Total |  |  |  |  | 21 | KF122 (2305744) Total |  |  |  |  | 35
[6 empty] | LW051(2311537) | Flow controller | 6500-T6-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-08-01 | 2 | Qty (2) shipped 6/22/22
[6 empty] | LW051(2311537) Total |  |  |  |  | 2
LY051 | Flow controller | 6500-T4-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-22 | 1 | LY051(2311533) | Flow controller | 6500-T4-F04-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-22 | 1
LY051 Total |  |  |  |  | 1 | LY051(2311533) Total |  |  |  |  | 1
PN051 | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6 | PN051 (2311537) | Circuit Breaker | ZEK35-UL | Eaton | 2022-07-22 | 6
| Filter Housing bowl | YY66B2280 | ENTEGRIS | 2022-12-22 | 5 |  | Filter Housing bowl | YY66B2280 | ENTEGRIS | 2022-12-22 | 5
| Flow controller | 6500-T2-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-11-10 | 1 |  | Flow controller | 6500-T2-F03-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-11-10 | 1
| Valves | 201-46-01-3 | ENTEGRIS | 2022-09-22 | 2 |  | valves | 201-46-01-3 | ENTEGRIS | 2022-09-22 | 2
|  | DS12-2C-12F-3 | ENTEGRIS | 2022-08-04 | 16 |  |  | DS12-2C-12F-3 | ENTEGRIS | 2022-08-04 | 16
|  | NVT4-T4-2 | ENTEGRIS | 2022-08-26 | 4 |  |  | NVT4-T4-2 | ENTEGRIS | 2022-08-26 | 4
PN051 Total |  |  |  |  | 34 | PN051 (2311537) Total |  |  |  |  | 34
RV041 | Circuit Breaker | ZEK35-UL | EATON | 2022-07-22 | 6 | RV041D(2311536) | Circuit Breaker | ZEK35-UL | Eaton | 2022-07-22 | 6
| Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5 |  | Filter Housing | YY6620A2FE | ENTEGRIS | 2022-10-27 | 5
RV041 Total |  |  |  |  | 11 | RV041D(2311536) Total |  |  |  |  | 11
VC121D | Flow Controller | 6500-T1-F02-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-06-16 | 1 | VC121D (488050) | Flow controller | 6500-T1-F02-D12-K-P7-U3 (1.1) | ENTEGRIS | 2022-07-17 | 1
VC121D Total |  |  |  |  | 1 | VC121D (488050) Total |  |  |  |  | 1
Grand Total - EMD |  |  |  |  | 205 | Grand Total - TPC |  |  |  |  | 217