## January
Date | Tool | Task | TECH
2025-01-02 | FU151D | Installed FT001, FT002, FT003, FT004, FT014 | JM
2025-01-02 | JP151D/FU151D | Looking for parts for NCSR to install. Parts are in another room with less lighting.
2025-01-03 | JP151D | FC021 Installed | TW
2025-01-03 | FU151D | FC021, 022, 023, 025,026, 027 installed. Tool ID tags installed(removed intel stickers with updated placards from finishing kit) | JM
2025-01-03 | FU151F | FT002 installed in feed. Tool ID tags updated as well | JM
2025-01-06 | JP151D | FT004 and FT014 installed for filter station | CJ
2025-01-06 | FU151D | Installed AE025. Wrote RMA for cables for AE023 and AE025 | DS
2025-01-06 | BT151 | Completed Hand over Hand in Most compartments. Prepped the tool for testing. | TW
2025-01-06 | JP151D | Find parts for the FC per Intel spec for upgrade. Chem 1 - 3/8" 0-1250 mL/min. and Slurry - 1/2" 0.25 L/min. Found all parts and Installed the chem 1 - 1/2" 0-1250 mL/min. per intel. Finished installing all FC'S
2025-01-07 | FU151D/F | Completed Hand over Hand. Installed FT002 in Feed and AE023 in Blend | DS
2025-01-07 | BT151 | Completed the Hand over Hand inside the Chaseway. | TW
2025-01-07 | JP151D | Continue to install NCSR parts and Intel spec parts on Blend. LPC and AT025.
2025-01-08 | TM151D | Troubleshoot pump one, Found that the Interface connection was the issue. Removed interface from WL152D and installed it on TM151D. Also, noticed the 1-IY connection on 5 was not releasing. It was stuck. I had to cut wire and remove 1-IY from WL152D. | DS/RD
2025-01-08 | BT151 | Double checked the Hand Over Hand | TW/CJ
2025-01-09 | TM151D | Calibrated pump 1 IYs | DS/RD
2025-01-09 | FU151D | Continued startup checklist | DS
2025-01-09 | JP151D | Continue install on non-dilution and CR288.
2025-01-09 | WR151 | Finished Electrical connections on all flowmaster tools between Distribution and Blend. | CJ
2025-01-09 | JT151 | Bends and connections made from the... | CJ
2025-01-10 | JP151D | Install the single dilution on the Blend. | RD
2025-01-10 | JT151 | LPC installed and capped. | CJ
2025-01-11 | JP151D | Continue to work on the single dilution. Inspected tanks and found Tank 1 cracked.
2025-01-11 | FU151D | Continued startup checklist, checked all valves and pressure tested loops | DS
2025-01-13 | TM151D | Re-calibrated pump 1 IYs per Intel request | DS
2025-01-13 | FU151D | Continued startup checklist | DS
2025-01-14 | FU151D/F | Continued startup. SOOs and fixed small leaks. Feed complete | DS
2025-01-14 | FU151D | Completed Startup, wrote FSR | DS
2025-01-14 | HG151 | Installed NCSR flow controllers | TW
2025-01-14 | JT151 | Wrote RMA for AE025 | TW
2025-01-14 | JP151F | Hand over hand complete | CJ
2025-01-14 | JT151 | Hand over hand complete | CJ
2025-01-14 | JP151D | Create an RMA for Tank 1 that is cracked found on 1/11/25. Sent emails. | RD
2025-01-15 | HG151 | NCSR AE025 install, Pulled part from JP151D Kit. | RD
2025-01-15 | JP151D | Remove Tank 1 from RR152D. Remove Tank 1 and place to side Install tank from RR152D. Flare line connections on Feed station. | RD
2025-01-16 | HG151F | Began startup | DS
2025-01-16 | KOR151D | Replaced FC001 that was removed from KF152D. Flush the FC001 with UPW for Decon and Create RMA. Bernie Klees wants to verify a full decon before sending back. | DS/RD
2025-01-16 | EF151D | Replace wire harness and connected AT025 to terminal and breaker. | CJ
2025-01-16 | HG151D | Worked on installing NCSR Parts. | CJ
2025-01-17 | JT151D | Train FSE Casey James how to torque and remove and replace gaskets on an M960 pump. Continue to flush the McMillan from KOR151D Decon before sending back, | RD
2025-01-18 | JP151D | Continued on start up on feed and Dist. Pressure test from Feed to Dist. and Dist. Loop 1 and Loop 2. | RD
| HG151F | Continued startup checklist. Filled tank and loop to the blend
2025-01-21 | JP151D | Continue start up on Blend and Dist. Cut back a couple inches on the electrical flex conduit on Tank 1 and Tank 2. Show Casey how to do. | RD/CJ
2025-01-21 | BT151D | Pull pump out of DT1 and DT2 torque pump. Change gaskets on the bore caps and inlet and outlet. | CJ
2025-01-22 | BT151D | Walk Travis through how to pressure test Supply line and Return on a chem blend. Intel had done previous Chem Blend pressure tests. This was his first pressure test he has done by himself and walking with intel on the supply line in sub-fab and return. | RD/TW
2025-01-22 | JP151D | Continue to work on start up. | RD
2025-01-22 | BT151D | Pressure test complete | TW
2025-01-22 | HG151D/WR151D | Panduit adjusted for dinrails | CJ
2025-01-22 | HG151D/WR151D | Tank 1 and Tak 2 Electrical lines cut back | CJ
2025-01-22 | HG151D | Hand over hand complete on blend | DS
2025-01-23 | BT151D | Disabled the Supply return, was not supposed to have it. Capped/plugged both ends. Checked all facilities are working on the tool in preperation for putting it in process. | TW/CJ
2025-01-23 | JP151D | Continue Start up. | RD
2025-01-23 | HG151D | LPCs installed, Hand over hand complete on distribution | DS
2025-01-24 | JP151D | Continue Start Up. | RD
2025-01-24 | HG151D | Tested all CVs and pressure tested loops. Began checklist | DS
2025-01-25 | JP151D | Finish start up | RD
2025-01-27 | HG151D | Blend and Distribution alarms and SOOs
2025-01-27 | JP151D | Calibrate pumps and Connect wiring for the FC030. Start the FSR. | RD
2025-01-28 | EK151D | Install NCSR Parts, FC021, FC022, FC023, FC025, FC026, FC027 Chancged to Intel Spec on UPW, Slurry and Chem. Placed previous flow Controllers in cage. Used FC from JP151D. Aaron B. | AB
2025-01-28 | KG152D | Dan wants the tool to be prepped for start up, LPC: electrical connection to j-box, electrical connectors, PV005 Mian OFA. | CJ
2025-01-28 | WR151D | Dan wants the exhaust fixed with upgrade on Feed and Blend chaseway area. Sending emails for parts installed information. | CJ
2025-01-28 | JP151D | Continue on FSR. Help Casey, Aaron and Travis on parts needed for installs on tools. | RD
2025-01-28 | GR151D | Intel wanted the Flow Controller changed on the Chem from 0-250 mL to 0-500mL. | TW
2025-01-28 | Phase 1 | Hazardous Control for Phase 1 - Update on shared drive. | TW
2025-01-28 | HG151D | Finishing checklist and troubleshooting PV030. Fixed leaks on KV012 and DFC02 | DS
2025-01-28 | BT151D | Finished BT | TW
2025-01-29 | HG151D | Troubleshooting PV030, replaced HV035(from HG152) for leak, fixed leak on DFC02 | DS
2025-01-29 | JP151D | Send email on SMC Flow Controllers for the PV030, FC030,CV030, FT030. We need to set up and calibrate with correct software. | RD
2025-01-30 | HG151 | Completed startup, Change FC022, FC023, Slurry and FC026, FC027 Chem per Intel Spec. Pulled flow controllers from Fab 42 cage. 1/2" for slurry and 1/2" KV03 and KV07 pulled from RR152D. | DS
2025-01-30 | JP151D | FSR Signed for completion. | RD
2025-01-30 | KG151D | Install PV005 parts pulled from KF152D. Meeting with GCS. | TW
2025-01-30 | WK151D | Exhaust HPM Mod. And get parts from Chandler Office. Get 4" hole saw from Intel. | CJ
2025-01-30 | WK151D | Intel pointed out that the contractors broke the mount for the Electrical disconnect on Feed. Need to reweld. No Live power on this tool. It is LO/TO from the breaker. | DS/RD
2025-01-30 | EK151D | LPC's installed and AE025 installed on Blend. Continue on NCSR parts installed in Dist. | AB
2025-01-31 | HG151 | Troubleshooting PI012 broken needle due to water pressure hammering | DS
2025-01-31 | KG152D | Fixed leak on PV005 and leak checked. Conducted Electrical Hazard checklist | TW
2025-01-31 | EK151D | Installed pressure transducers | AB
2025-01-31 | WK151D | Installing exhaust modification for HPM upgrade | CJ/RD
2025-01-31 | Other | Meet with Sung Moon to pick up lap top for SMC set up and install. | RD

## Febuary
Date | Tool | Task | TECH
2025-02-01 | EK151D | Tighten fittings on Dist. Start installing NCSR parts on Feed station. | RD
2025-02-01 | WK151D | Finished installing the exhaust modification | RD
2025-02-01 | All Dist. Tanks | Cut back the plastic on the Dist. tanks and Feed tanks. Trip hazard. | RD
2025-02-03 | EK151F | Installed FT001 and FT002 and made some adjustments to the PFA lines. | RD
2025-02-03 | WC151D | Swapped flow controllers to Intel spec. FC021, FC022, FC023, FC025, FC026, FC027 were replaced. Making 1/2" lines for FC022 and FC026. | DS
2025-02-03 | JP151D | Made adjustments and cut the 1" PFA line on the atomizer due to not draining. | RD
2025-02-03 | WK151D | Adding NCSR Parts FC021, FC022, FC025, FC026 | CJ
2025-02-03 | JT151D | Verified and installed LPC | TW
2025-02-04 | WC151D | Installed NCSR parts. Flow controllers, AE/AT030, and FT030 | DS
2025-02-04 | KG152D | Adjusted pressure switches and started checklist | TW
2025-02-04 | EK151D/Other | Cut back the flex lines on the Dist. Tank 1 and 2. Go to Chandler site to get SMC cable and update Time, Training and send emails. | RD
2025-02-04 | WK151D | Worked on exhaust mod for the blend unit. | CJ
2025-02-05 | WC151F | PV004 leaking from weephole. Swapped with regulator from HG152. Hand over hand complete. | DS
2025-02-05 | EK151D/Other | Hand over hand on the Blend and Dist. Meet Ken for the SMC cables to check if compatble with laptop and software. Go to Chandler site to pick up electrical cord for LPC (Qty. 3). | RD
2025-02-05 | Other | Updated feed procedure | TW
2025-02-05 | WK151D | Finished upper half of exhaust modifications | RD
2025-02-05 | WK151D | Working on adding more mods to exhaust mod on blend station | CJ
2025-02-06 | Other | SMC class | TW\DS\RD\CJ
2025-02-06 | JT151D | Installed LPC, Pressure Test Supply Loop, Confirm all CV's, begin Alarm Testing. | TW
2025-02-06 | JT151D/NCSR | Re-teflon tabed Atomizer parts, Helped confirm JT CV's and alarm test | CJ
2025-02-06 | EK151D | Hand over hand on the Feed station. Check electrical on the Blend/Dist and Feed. | RD
2025-02-07 | WC151D | Finished atomizer line, completed hazardous energy checklists. Found broken valve base, RMA written | DS
2025-02-07 | EK151D | Pressure test Loop 1 and Loop 2. Check under Tank drain for inspection. | RD
2025-02-08 | EK151D | Check tanks, Hand over Hand, Go over the Start up procedure. | RD
2025-02-10 | EK151D | Had a leak on loop 2 and Intel check the loop. Intel wanted to check with UPW since they could not find the leak. The leak was at the Loop 2 supply out from the Dist. 1' elbow was cock eyed on fitting. Fixed | RD
2025-02-11 | WC151D | Hand over hand on Blend/Dist. Checked Dist tank drains. Replaced CV086 base with base from RR152 | DS
2025-02-11 | EK151D | Start up for the Feed station. Had to dump out the drum UPW 2X'S due to particles floating around in the drum. Had a non-compression fitting off the main OFA manifold that feeds to the CV014/PI014. | RD
2025-02-12 | WC151F | Landed Tank electrical. Bent new tank line. Started checklist | DS
2025-02-12 | WL151D | Installed LPC | CJ
2025-02-12 | EK151D | Had issues witht the Alarm history and Event history. Would not capture right away. Noticed on the last tool of JP151D. This is on all systems, FlowMasters and Chem Blend. Notified Olivia and Bernard. | RD
2025-02-13 | WC151 | completed tank drain checks and programmed level sensors. | DS
2025-02-13 | other | Updating checklists | TW
2025-02-13 | EK151D | Finished with EK151D. Need to create RMA for parts broken. | RD
2025-02-14 | EK151D | Drain the UPW Drum and Clean up area of EK151D. | RD
2025-02-14 | WC151F | Worked on checklist, pressure tested loop.
2025-02-15 | WR151 | Start the Start up on tool, Go ever hand over hand on Blend and Dist. Performed tank inspection and found a crack on tank 2 with other issues. Cleaned the bottom of the tank stand. Re flare 1" lines. | RD
2025-02-17 | Other | Update FSR for overtime. Go through PCD Documents and RMA with Travis and Casey. | RD/TW/CJ
2025-02-17 | WC151F | Fixed leak found at fitting on bottom of feed tank. Found that the feed loop is landed incorrectly at the blend. Discovered that the supply and return are swapped at the blend unit
2025-02-17 | WC151D/F | Trades fixed the lines that were swapped. New pressure test completed. Blend/distribution checklists started | DS
2025-02-17 | BT152D | Hazardous energy control completed. Fixed commons door level. | TW
2025-02-18 | Other | Finished installing all the automizers, automizer replacements completed | CJ
2025-02-18 | EK151D | Signed off for tool finished. Update RMA for EK151D. | RD
2025-02-19 | WC151F | Completed Feed checklist except tasks requiring network. Wrote track and trend RMA for leaking feed tank. Delivered UPW regulator PV004 RMA | DS
2025-02-19 | other | Delivered NCSR LPC and had FSR signed.
2025-02-19 | WL151D | Installing all NCSR parts LPC, FT030, | CJ
2025-02-19 | WR151D | Hand over hand on Feed. Re flare the tank supply from cabinet. Place cover back on the blend for LPC. | RD
2025-02-20 | WR151D | Reflare 1'' line on Atomizer and Feed lines.
2025-02-20 | WC151D | Loop 2 pressure test complete. Loop 1 fails pressure test, will walk loop with Intel. Blend and Feed LPCs removed and put in Intel cabinet per Intel | DS
2025-02-21 | WC151D | Found loose connection on Loop 1 causing pressure test failure. Fixed by trades. Flowed both loops with UPW. Troubleshot FC023 bad transmitter, MCB13 was not making good connection | DS
2025-02-24 | WC151D | Tested blend and distribution alarms. Worked on SOOs | DS
2025-02-24 | BT152D | Replaced HV121 with valve from KF152 due to leaking from weephole. Tested CVs | TW
2025-02-24 | WL151F | Inspected drain line | CJ
2025-02-25 | WC151D | Completed checklist except checks that require network. | DS
2025-02-25 | WR151D | Hand over hand Dist. and Blend. Check drain manifold on Tank 1 and Tank 2. Set Flowline sensors on Tank 1 and 2. Check AOV's Opend and Close. | RD
2025-02-26 | WL151D | Completed Hazardous energy checklists and modified distribution panduit | DS
2025-02-26 | BT152D | Completed checklist. Needs Main OFA regulator replaced | TW
2025-02-26 | WR151D | Hand over hand on Feed station, Pressure test Loop 1, Loop 2, and Raw slurry to Blend. Check drain manifold on Feed tank. Set Flowline sensor on Feed Tank. | RD
2025-02-27 | WL151D | Completed hand over hand and started checklist | DS
2025-02-27 | WK151F | Working with Dan on WK151F mods and double containment lines | CJ
2025-02-27 | Other | Update RMA matrix, Start FSR for WW8. Update passdown, APT's and SAP. | RD
2025-02-28 | WR151D | Start SOO on Feed.
2025-02-28 | WL151F | Pressure tested feed loop, Set Levitronix level sensor | DS

## March
Date | Tool | Task | Tech
2025-03-01 | WR151D | Complete Start up. | RD
2025-03-03 | WL151F | Worked on Feed checklist, installed missing HV021 tag and started blend/distribution checklist | DS
2025-03-03 | WR151D | Finish FSR. | RD
2025-03-04 | WL151D | Pressure tested and filled lines. Began Blend checklist | DS
2025-03-04 | HD151D | Started hand over hand | TW
2025-03-04 | WK151 | Flare secondary containment line for SLR inlet and Distribution loop return on the feed station. Run the 1" line and flare fitting inside the feed station to make connection. Work with contractors for parts needed to hold the secondary containment line in place. | RD/CJ
2025-03-04 | JP151F | Found wiring for FT002 that was landed in wrong area on 1AI. The flow was maxed out at 60 psi and would not go to zero when not in use. | RD
2025-03-05 | WC151 | Installed plugs on unused LPC lines | DS
2025-03-05 | WL151D/F | Completed Feed checklist. Working on SOOs for blend and distribution
2025-03-05 | WR151D | Flare the 1'' lines from the tank. Had a hard time flaring so decided to switch to primelock. Go to FAB 42 to find connections. | RD/CJ
2025-03-05 | AR151D | Installed NCSR HMI(formerly BT154)
2025-03-05 | CVB | Assist Mke Southwell weld a CVB in Sub-fab | RD
2025-03-06 | WL151D | Finished checklist. Found AT028 wired incorrectly - RMA written | DS
2025-03-06 | WR151D | Connect the 1" lines to tank for spray ball valve and tank process to feed station. Flare, cut and bend needed. | RD/CJ
2025-03-07 | WK151 | Completed Hazardous energy checklists. Trimmed distribution tank electrical lines. | DS
2025-03-07 | KF151/HD151 | Installed flow controllers and interconnects between day tank and delivery train | RD
2025-03-08 | RE151D | Installed NCSR Parts, Hand over hand on Dist. and Blend. Cut the flex conduit lines for the Dist tank 1 (2") and tank 2 (1-1/2") that connect to the J-Box. | RD
2025-03-10 | WK151 | Working on HPM upgrade checklist | DS
2025-03-10 | RE151D | Hand over and hand on the feed station, Clean the Feed station. Place the UPW drum on feed station. Reflare the 1" connection from tank to feed station (Supply). Check the tank drain manifold. | RD
2025-03-10 | HD151D/KF151D | Calibrated Pumps | TW
2025-03-11 | WK151 | Continued HPM upgrade checklist | DS
2025-03-11 | RE151D | Hazardous checklist on Feed and Dist. Check the drain manifold for Tank 1 and Tank 2. Wipe down systems of debris. Electrical inspection in Feed and Dist. Component inspection and blue tag. | RD
2025-03-11 | HD151D | Finished Hand Over Hand, Supply Return Loop Pressure test, | TW
2025-03-12 | WK151 | Continued HPM upgrade checklist
2025-03-12 | HD151D | Troubleshoot leak in DT1, Ordering RMA's on 11 ChemBlend Filter Housings, Create RMA for GR151D CV203 leaking and BT152D FL202 leaking. | TW
2025-03-12 | RE151D | Pressure test Loop 1 and Loop 2. Pressure test feed station. Intel ran UPW for samples. Update RMA Matrix. Troubleshoot HD151D w/ Travis on leak. | RD
2025-03-13 | WK151 | Worked on startup checklists on feed, blend and distribution. Programmed tank level sensors | DS
2025-03-13 | RE151D | Start on Feed station and Finish feed station. Start on Dist and Blend. | RD
2025-03-13 | HD151D | Assist Travis on changing filter o-ring on HD151D. | RD/TW
2025-03-14 | RE151D | Start up check list for Dist. and Blend. Get confirmation from Dan L. Which tank to swap for Tank 2 (Tank has a crack).
2025-03-14 | WK151 | Pressure tested feed loop. Checked all CVs. Fixed loose fittings at Blend HV030 and Feed HV002. Made Distribution atomizer line. | DS
2025-03-17 | WK151 | Fixed leak on return line, replaced crossthreaded fitting. Filled tank and flowed loop. Feed alarm testing
2025-03-17 | RE151D | Removed Tank 2 from HG152D (Old FA151D) to place on RE151D Tank 2 (Crack on Tank 2). Replaced tank stickers from one tank to the other. Fill tank with UPW and test on one tank mode. | RD
2025-03-17 | WK151D | Drilled holes for the Drip pan in distribution for HPM drip pan, tied with zip ties. Got measurements and photo's for pan, sent to Kai for design input. | CJ
2025-03-18 | WK151 | Pressure tested distribution loops and charged system. Continued feed and hpm mod checklist. | DS/AB
2025-03-18 | RE151D | Signed off FSR and worked with intel on bad FT002 on the feed station. Removed the RMA from RFT152F NCSR PARTS. Placed box inside the unit stating why it was pulled. Received correct spec from Intel for RR151D. | RD
2025-03-19 | RR151D | Start installing the NCSR parts and replace FC021 and FC025 from 0-10 L/min. to 0-20 L/min. for correct spec. Pull Analytical parts from Fab 42 to install RR as a single dilution. | RD
2025-03-19 | WK151D | Replaced CP02 with CP02 from RAK152, RMA written. Continued checklist | DS/AB
2025-03-20 | WK151D | Continued checklist. Following up on HPM checklist with engineering. Replaced FT030, PV015, and PI012 with parts from RAK152 | DS/AB
2025-03-20 | RAK152 | Seperate NSCR parts, Checked with Intel with correct flow controllers, Record all SN & parts down. NCSR can be installed. | CJ
2025-03-20 | RR151D | Installed analytical, LPC for the blend
2025-03-21 | WK151D | Continued checklist on Blend/Dist ,ontinued to troubleshoot HPM mod on feed( no sample button) | DS/AB
2025-03-21 | RR151D | Finish installing analytical, LPC for the Blend. Hand over hand on the blend.
2025-03-22 | WK151D | Trouble shooting photohelic on feed | AB
2025-03-22 | RAK151D | Started hand over hand on Feed | AB
2025-03-22 | RR151D | Hand over hand on the Feed and Dist. Calibrate Feed and Dist. tanks. Check tank drain manifold on Feed and Dist.
2025-03-24 | RR151D | Check the electrical hazard and electrical for the LPC and analyitcal. Check MV and AOV's. Pressure test the feed, loop 1 and loop 2 of Dist. Start the function test on Feed station.
2025-03-24 | RAK152D | Installed Flow controllers (FC021, FC022, FC023, FC025, FC026, FC027) | CJ
2025-03-24 | RFT152 | Track NCSR parts for this tool to install at a later time. | CJ
2025-03-25 | RR151D | Start SOO's on Feed, Dist. and Blend.
2025-03-24 | AR151D | Found All the NCSR and missing parts for AR151, confirmed with the audit sheet, and cleaned the tool in preperation for installation. | AB
2025-03-24 | RAK151F | pressure testing loop to Blend | AB
2025-03-24 | WK151F | Trouble shooting photohelic and sample function with Eng. | AB
2025-03-25 | RAK151F | System charged with water, running function testing | AB
2025-03-25 | WK151F | Trouble shooting photohelic and sample function with Eng. waiting on new HPM alarm testing checklist | AB
2025-03-25 | RAK151D | Pressure tested distribution loop after Intel made loop sizing adjustment test passed | AB
2025-03-25 | WK151D | Finished fabricating and installed drip pan on Blend system / searched for new tubing for photohelic. | AB/CJ
2025-03-25 | WK151D | Tapped and installed HPM drip pan in blend station along. | CJ
2025-03-26 | WK151D | Ran tubing between the exhaust and blend system to the photohelic. | CJ
2025-03-26 | RR151D | Finish SOO's and 3/4 Finish with Dist. and Blend SOO's. I had to change blend from a single dilution to non-dilution and be finish by the end of the day. | RD
2025-03-26 | AR151D | Started hand over hand on Feed
2025-03-27 | RR151D | Finish testing and turn over to Intel. | RD
2025-03-27 | AR151D | Started hand over hand on Feed
2025-03-28 | RR151D | FSR signed off.
2025-03-28 | Other | Look for parts at fab 42 for the FPE, 2 Chem rinse power supply upgrade 10V for KOR141D and KOR142D. 3 IY for DSS22 CPO1 & 4, RAK111 CP03. Get a solenoid for Aaron to replace on AR151D. | RD
2025-03-29 | Other | Update FSR for overtime.
2025-03-29 | XJ151D | Wipe down system and connect the 1" spray line line from chaseway to tank 1 and tank 2. Cut 2" off the tank 1 speay connection and reflare it was a little long. Found a leak from the main UPW connecting to Blend. Report leak to intel.
2025-03-31 |  | Track NCSR parts and verify if they are correct for tools KOR152D, BH152D, RFT151D, placed them inside tool for install | CJ
2025-03-31 | XJ151D | Ask for tool spec. Walk loop 1 and Loop 2 with Intel. Go to Fab 42 and get correct Flow controllers. Walk the tools down for FPE and get parts together.
2025-03-31 | RAK151D | removed SOL2 (broked Pin #3) installed new SOL2 | AB
2025-03-31 | WK151D | Working with Eng. to create new sample proceduer for HPM systems | AB

## April
Date | Tool | Task | Tech
2025-04-01 | KOR141D | 10 AMP Power supply upgrade with breaker | AB/CJ/RD
2024-04-01 | DSS22D | CP01/CP04 IY's replacment and calibrations removed parts from AK121D during troubleshooting | AB/CJ/RD
2024-04-02 | AK121D | Reinstalled parts that were removed during DSS22D troubleshooting | AB/CJ/RD
2025-04-02 | WK151F | Working with Eng. to create new sample proceduer for HPM systems | AB
2025-04-02 | Other | Received 6 filter houisng and 6 filter bowls for BT151D and AH151D. and pump WK151D CP02. | RD
2025-04-03 | RAK151D | Fixed small H2O2 leak in Blend, Charged loops, started funtion testing | AB
2025-04-03 | XJ151D | Hand over hand on Dist., Blend and Feed. Check the tank drain manifold on Feed and Dist tank 1 and 2. | RD
2025-04-04 | WK151F | Meeting with Kai about sample functions update on HPM | AB
2025-04-04 | RAK151D | Continue funtion testing.
2025-04-04 | XJ151D | Install correct FC found an M36 for FC21. Had an older model # that was pulled from Fab 42. But actually replaced from the RR151D. Identify blue tags and actuating CV'S on Dist. & Blend. | RD
2025-04-07 | XJ151D | Feed station identify blue tags and actuate CV's. Pressure test Dist. Loop 1 and Loop 2. Feed to Blend loop. | RD
2025-04-07 | RAK151D | Help with the SMC flow controller to calibrate and set up the Anton parr. Need to calibrate pumps per intel. | RD/AB
2025-04-08 | XJ151D | Calibrate the Dist. Tank 1, 2 and feed tank. Adjust the PS on Feed, Dist, Blend. Flow UPW through the loop and to the tanks. Start SOO's on Feed. No comm. | RD
2025-04-07 | XJ151D | Helped Raquel get the HMI working on XJ. Updated Chemrinse procedures with latest changes. | TW
2025-04-08 | RAK151D | Troubleshooting IY10 - repalced IY10 | AB
2025-04-08 | KOR142D | Work on NCSR and Hand over Hand | CJ
2025-04-09 | RAK151D | troubleshooting CP03 Flow calibration. Corrected calibrationand completed sign-0ffs | AB
2025-04-09 | XJ151D | Finish the feed SOO's | RD
2025-04-09 | KOR142D | Install NCSR parts to the correct line | CJ
2025-04-09 | KOR152D | Started connections between the delivery train and Day tank. Helped Casey and Raqel go through start up procedures. | TW
2025-04-10 | JK151F | Start up check list for feed. Facnet needs to be uploaded on HMI | AB/RD
2025-04-10 | XJ151D | Finish the Dist. and Blend SOO's Finished start up and need to fix leaks. SMC still not fixed. | RD
2025-04-10 | other | 1 Tank delivery | RD
2025-04-10 | WK151F | Relabel green SURRY to PROCESS CHEMICAL in feed station and outside lines. | CJ
2025-04-10 | KOR151D | Removed the filter compartment and all the work i did installing the lines between the Day Tank and Delivery Train. | TW
2025-04-11 | KOR151D | Power supply failed on 4PWS. When intel was starting up chemblend for first time. Intel provided part and installed. Notified Bernard, Jeff, Mike Meeting is set up on 4/14/25 for Power Supply incident.
2025-04-11 | JK151F | Pneumatic lines on solenoids were backwards / correctd and Continued funtion testing. Charged feed loop in manule. BAD LS001 sensor (Day Tank leak sensor) needs rebuild /replaced | AB
2025-04-14 | KOR151D | Had a morning meeting with Engineers of the Power supply incident.
2025-04-14 | JK151F | Found leak on weld of Feed tank. Swapped with tank from WL152 | DS
2025-04-14 | WK151D | Finish changing labels on the Feed station, Intel is charging chemical on system. Found PI012 broken on blend changed and create an RMA (This part was actually changed before) | RD
2025-04-15 | JK151F | Inspected tank, re-welded the hand valve support brackets. Wrote RMAs and continued startup | RD
2025-04-15 | XJ151D | Finish calibrating the SMC and finish writing FSR. | RD
2025-04-15 | Other | 2 tank delivery | RD
2025-04-16 | XJ151D | FSR Signed off. | RD
2025-04-16 | JK151D/F | Hand over hand, Go no Go on Dist & Blend, Tank inspection found damage on tanks 1 & 2 RMA created, Change FC's to intel spec. Did not install AE025/AT025 on Blend. Inspect drains on tanks. Dist. Din rail adjusted. Feed SOO's. | RD/CJ/DS
2025-04-17 | JK151D | Change tank 2 with one of the new tanks delivered per Intel. Tag inspection, Manipulate CV'S. Found blend Solenoid 1 pneumatic lines swapped A vs. B (fixed). Set the tank levels. Pressure test loop 1 and loop 2. Fill tank 2 with UPW to check fittings on tank for any leaks leave for overnight. | RD/CJ/DS
2025-04-18 | JK151D/F | Finish SOO's. | DS
2025-04-18 | Other | Update the RMA matrix and prep for parts to be returned. | RD/CJ
2025-04-21 | KT151 | Audit and gather flow controllers and parts. | DS
2025-04-21 | Other | Updating the RMA excel spreadsheet | RD/CJ
2025-04-22 | JK151 | Write FSR and have Intel sign | DS
2025-04-22 | Other | Updating the RMA excel spreadsheet. Shipped out the PV005 (2x's) and | RD/CJ
2025-04-22 | WK151F | Troubleshoot constant red alarm light. Found Electrical compartment prox sensor not triggering. Moved sensor closer, problem solved | DS
2025-04-23 | KT151 | Swap non-dilution to single dilution on the blend
2025-04-23 | Other | Updating the RMA excel spreadsheet
2025-04-23 | RFT151D | Set up RFT for testing, got paperwork printed out, NCSR Parts installed, audit sheet reviewed and cleaned tool of any plastic and trash including zip ties on internal parts. | TW
2025-04-24 | KT151 | Continued swapping to single dilution. Installed NCSR AE/AT025 | DS
2025-04-24 | Other | Updating the RMA excel spreadsheet | RD/CJ
2025-04-24 | RFT151D | Wrote down the Serian Numbers and information from HMI's on to the start up document. completed the hazardous energy control. levitronix software not communicating. USB in electrical | TW
2025-04-25 | Other | Updating the RMA excel spreadsheet
2025-04-28 | KT151 | Finished lines for Flow controllers and installed
2025-04-28 | BT151D | Assist Intel with changing the leaking filters. Changed out the head and bowl on DT1 - FL102. Could not get off the Head off of the FL101 on DT1. One out of the 4 bolts holding the head in place was galling. We will continue with DT2 tomorrow. | RD/CJ
2025-04-29 | KT151 | Made LPC drain line and air supply line(need 1/4" fitting to finish) prepped to install tank 1 | DS
2025-04-29 | Other | Steve Khun visited Fab 52 for Gas and PCD walkthrough and after was a company dinner.
2025-04-30 | KT151 | Installed Tank 1 and connected all interconnects. Found Tank 2 had a gouge in it
2025-04-30 | RFT151D/BH152D | Assist Casey and Travis on Systems crosstraining.
2025-04-30

## May
Date | Tool | Task | Tech
2025-05-01 | KT151D | Tank 2 replacement, Had issues with tank 2 install. Studs are a little too long. Waiting on Dan L. Suggestion. Measured the tank in 3 places. Not all same measurement. | DS/RD
2025-05-01 | WL152D | Had Intel order a PLC Interface for pump 1. Install IY 1 and IY5 for pump 1. Need to install and remove LO/TO. Contractors need to connect electrical. | RD
2025-05-05 | KT151D | Installed PI012 from RMA parts intended for HG152, PV015 from RAK152. 3 way valve base also installed from RAK152 | DS
2025-05-05 | Other | Don Maybe picked up the 6 filterbowls and 4 filter houisng. Waited for Intel to decon one more filter housing. When done take to office to prep for shipping. Answer questions from Brian Baker Entegris | RD
2025-05-06 | KT151D | Tightened Fast n tight fitting on Feed, checked tank and tank drain. Completed hand over hand on feed and pressure tested feed loop.
2025-05-06 | WL152D | Install the 1" to 3/4" reducer fitting in the Blend chaseway connection had to reflare 3/4" line to connect without kinking. Update the RMA Matrix. Received feedback from Brian Baker of sending filters parts back. | RD
2025-05-07 | KT151F | Completed feed checklist except on demand checks. Started blend checks | DS
2025-05-08 | KT151D | Completed last feed checks. Fixed leaks on LPC and Blend. Fixed wiring to FC030(was wired for FC029) | DS
2025-05-08 | RFT151D | Finish hand over hand on feed station and check list for valves. Pressure test loop from feed to Blend. | RD/TW
2025-05-09 | KT151D | Completed Distribution checklist. Waiting on customer if a AT028 is required. Need to fix leak on PV004 | DS
2025-05-09 | RFT151D | Pressure test passed from feed to blend. Connect UPW drum and Start filling loop with UPW and Start SOO'S. Finised SOO's | RD/TW
2025-05-12 | KT151D | Fixed leak and completed. No AT028 required per customer | DS
2025-05-13 | KT151D | Paperwork completed and signed by customer | DS
2025-05-13 | RAK152D | CP02 installed(from previous WK151 RMA). Installed NCSR AT/AE025, FT001, FT002, FT003, FT004, and FT014. | DS
2025-05-13 | RFT151D | Check loop 1 and 2 with Intel. Start pressure test on loops. Passed pressure test Fill loops with UPW and fill tanks. Start SOO'S on Dist. | RD/TW
2025-05-14 | RAK152D | Installed NCSR flow controllers, LPCs and FT030. | DS
2025-05-14 | RFT151D | Continue SOO's on Dist. and Blend | RD/TW
2025-05-15 | RFT151D | Assist Travis w. Calibrating pumps on Dist. | RD/TW
2025-05-15 | Other | Attend meeting with EMD ELectronics. | RD
2025-05-16 | RAK152F | Installed NCSR FT001 and FT002 | DS
2025-05-16 | JP151F | Non compression fitting blew off on feed unit. Replaced and wrote RMA | DS
2025-05-16 | RFT151D | Start and Finish FSR - Dan Lasley did not sign
2025-05-19 | RAK151D | Installed PV005 and PI012 | DS
2025-05-20 | RAK151F | Installed PV009 from RMA | DS
2025-05-20 | GR151D | Installed CV203. Have bad part in grey cabinet. This part had no chemical. Resend email to update RMA. | TW
2025-05-21 | RAK152D/F | Completed hand over hand. Installed non compression fitting in feed leading to PV010 - taken from HG152F | DS
2025-05-21 | WL152D | Installed retaining clips on Sensor for Tank 1 LS004 and Feed Tank LS001. | DS
2025-05-21 | Other | Received the golf cart from A-1 for the EMD Electronics. Get an inspection from Rick Vines then receive the golf cart permit. Send information to Mike. | RD
2025-05-21 | Other | Start inventory on parts for Fab 32. | RD
2025-05-22 | RAK152D/F | Started checklists. Checked all CVs on feed and blend. Pressure tested and filled feed loop. Filled Feed tank | DS
2025-05-22 | Other | Go to office to get decals for cart and get lock for charger on cart. Place stickers on cart mandatory. | RD
2025-05-23 | Other | Dan wants and inventory of the Feed station for GEMU Replacement and Solenoids installed. Dan ordered parts that are needed. | RD
2025-05-23 | Other | Installed EF151D HGO2 spray hook and Tank 2 black handle. | RD
2025-05-27 | HD152 | Connected all lines into the Day Tank from Delivery Train, Installed Flow Controllers. Helped with setting up Feed Tank for welding. | TW
2025-05-27 | Other | Assist Juno O. with setting up tank for weld. Once the tank is done welding placed the tank back on tank stand. Place lid and fitting back on tank to fill with UPW to test weld. Leave overnight to see if any leaks. | RD/JO
2025-05-27 | RFT151F | Weld the tank bracket on RFT151F (Need to close the RMA Submitted) | RD/JO
2025-05-28 | HD152 | Connected Pnumatic lines, and lines going into the top of the day tank. Connected and set up SO2. Tighted Filter comp filters.
2025-05-28 | Other | Checked the tank for the weld found no leaks. Drained tank and place tank back on tank stand. Weld the brackets for the valves back in place. | RD/JO
2025-05-28 | Other | Contact Dan Mayhofer to weld the door brackets back in place of 311-T-BLU21-AU12-S. Had a hard time looking for an outlet. found one and had to use a long extention cord to location. Finished weld and contact Dan M. to test the door opening and closing. All was good. | RD/JO
2025-05-28 | RAK152 | Re-bent line in distribution, was starting to snakehead. Installed calibration bulkheads. Taken from HG152D, one of those was broken. Tried to take from Feed, one broke the other was crossthreaded. Took from RE151F | DS
2025-05-28 | RAK152 | Completed all checks requiring chem, Intel wants to turn on chem today.
2025-05-28 | RAK152 | Troubleshoot FT030 bad transmitter alarm. Wire checks completed and continuity good. Swapped FT030, PC030, 1IY(power indicator light off, taken from RFT152), and PLC board. Applied mA to PC030 connector and cleared alarm. Problem must be in the connector or the PC030 itself, even though the PC030 was swapped
2025-05-29 | AK121F | Start gathering parts for Solenoid upgrade. Give inventory to Dan on parts needed. Contact person for tool Eric Petronella. | RD
2025-05-29 | AK121F | Start bending 1/4" SS lines for Solenoid installs. Make labels. Drill Cover for electrical cord. Finish prepping. | RD
2025-05-30 | AK121F | Contact Eric Patronella for tool LO/TO. Start removing parts and installing mounts for solenoid. | RD

## June
Date | Tool | Task | Tech
2025-06-02 | AK121F | Install solenoids and SS connections. Need to update Eric of the CP01 OFA line has a hole and to replace. Found a UPW leak before the CV011. | RD
2025-06-02 | HD152D | Replaced PV005 on HD152D (Which was an RMA Replacement) with a different RMA Replacement RMA. Finished FSR/CofA on tool | TW
2025-06-03 | AK121F | Connect the electrical for the solenoids and run all the pneumatic lines to valves and test with Intel. All is working well. | RD
2025-06-03 | Other | Tool uncrate UQ151D (KT141D) | TW
2025-06-04 | Other | Tool UQ151D (KT141D) delivery to F42 Chemical dock. Set tool in place in Fab 42 PCD room and feed room. | RD/TW
2025-06-04 | RAK152 | Troubleshoot Bad transmitter alarm. Asked engineering for help. Continued Blend and Dist checklists. Completed Feed | DS
2025-06-05 | RAK152 | Helped Duane fix the SMC issue
2025-06-05 | RAK141D | Connect all the tank connections, had to recut and flare. Flare and rebend lines to tank 1 and 2. Connect all flex lines for electrical conduit | RD
2025-06-06 | RAK141F | Work with Contractors to fix unistrut on feed station. The unistrut is sitting too low for the tank PFA Connections from tank to tool. | RD
2025-06-06 | RAK152 | Completed checklist, RMA written for SMC issue. Paperwork | DS
6/6/20205 | KF152/HD152 | Extended photohelic air lines in chaseway per customer request | DS
2025-06-09 | HG152D/F | Installed NCSR and RMA parts FC021, FC025, AE/AT025 Blend. Installed PV004 and FT001 in Feed | DS
2025-06-10 | HG152D/F | Installed RMA PV015 on Blend. Installed NCSR FT002 in Feed and re-bent line for it. Discovered blend spray gun leaks by | DS
2025-06-11 | HG152D | Gathered parts and made new 1/2" lines for blend slurry flow controllers | TW/DS
2025-06-17 | HG152D | Installed Distribution Tank 2. Completed Hazardous energy checklists | TW/DS
2025-06-18 | HG152D/F | Remade kinked distribution tank line. Started feed checklist | TW/DS
2025-06-19 | HG152D/F | Pressure tested and filled feed loop. Filled Feed tank and all lines. | TW/DS
2025-06-20 | HG152D/F | Hand over hand on Blend and Distribution completed. Blend still missing Calibration tube bulkheads. Continued checklist | TW/DS
2025-06-23 | HG152D/F | Callibration tubes x3 taken from RAK152F per Intel. Loop 2 pressure test good. Loop 1 losing pressure, Intel found leaking valve and replaced. Pressure test good. Tool and loops filled with water, testing alarms | TW/DS
2025-06-24 | HG152D/F | Tested alarms and SOOs. Completed startup. Notified intel that trades need to cap fittings on top of feed unit. Blend HV035 slight leak from weephole | TW/DS
2025-06-25 | HG152D/F | Writing RMAs and FSR for startup | DS
2025-06-30 | WL152F | Installing Feed tank and lines | DS

## July
Date | Tool | Task | TECH
2025-07-01 | WL152F | Re-bent and installed Feed tank lines | DS
2025-07-02 | WL151D | Started installing finishing kit in blend unit. Installed PD01, FC030, FT030, CV030, and needle valves | DS
2025-07-03 | WL152D | Continued installing finishing kit. LPCs removed per Intel. Installed lines and ST01 | DS
2025-07-07 | WL152D | Installed AT025 and AT028 | DS
2025-07-08 | WL152D | Installed AT023 and wiring | DS
2025-07-09 | WX121F | Uninstalled Back Pressure Controller. No Slurry Drain, tniy hole in the bottom of tool leading to grated flooring, so needed to find a way to stop the tool from siphoning water out and flooding the tool when the bpc was disconnected. Had to drain Tank little below Half. Located the Parts to install to PBC, and solenoids. | TW
2025-07-09 | WL152D | Installed flow controllers and lines. Re-bent as necessary | DS
2025-07-10 | WX121F | Installed Back Pressure controller into tool. prepped the cable and plugged in the wiring. | TW
2025-07-10 | WL152F | Installed FT001 and FT002, re-bent lines | DS
2025-07-11 | WL152D/F | Prepped 1MC user interface for install. Removed HV013 and non compression fitting from KT141 to use in WL feed
2025-07-11 | WX121F | Uninstalled solenoids, and Chiseled blocks in the way of placing new solenoids. | TW
2025-07-14 | WX121F | Scavengar hunted for the parts required to complete the solenoid upgrade. Still need 1/4' Stainless Steel. Made labels for solenoids. | TW
2025-07-15 | WX121F | located stainless steel lines and e. Welded B
2025-07-16 | WL152D/F | Wired 1MC user interface in distribution. Fixed leaks on Feed tank fittings | DS
2025-07-17 | KOR143 | Set tool with intel. Installed chaseway bolts | DS
2025-07-17 | WL152D | Continued checklist | DS
2025-07-17 | WX152X | Installed the stainless steel for the solenoids. | TW
2025-07-18 | WL151D | fixed leak on atomizer. pressure tested, filled loops and tanks | DS
2025-07-21 | WL152F | Completed feed Checklist | DS
2025-07-21 | WL151D | Continued Blend and Dist checklist. Calibrated 5IY. Fixed AT028 wiring, RMA to be written | DS
2025-07-22 | WL152D/F | Startup complete, writting RMAs and FSR | DS
2025-07-23 | XJ/EK141 | Move in and set tools | DS
2025-07-24 | XJ/EK141 | Finished setting tools | DS
2025-07-24 | WL152 | FSR and startup paperwork signed and put in folder | DS
2025-07-25 | RFT152D | Prepped Tank 1 for removal. Installed FT001,002,003,004, and 014 | DS
2025-07-28 | RFT152D | Installed flow controllers, re-bent 1/2" lines | DS
2025-07-28 | RFT152F | Installed NCSR FT001, FT002. Installed PI004 | DS
728/2025 | KT141 | Installed NCSR Parts | TW
2025-07-29 | KT141/WL153 | Connected Conduits from Chaseways.
2025-07-30 | multiple | Received 3x NCSR LPC and RMA parts. RMA parts and NCSR paperwork in cabinet | DS
2025-07-30 | RFT152D | Hand over hand on distribution, checked tank 2 drain, Re-flared 1/2" fitting on FL01 drain and replaced nut - jumping threads | DS
2025-07-31 | RFT152D | Printed paperwork and started checklists. Haz energy completed | DS

## August
Date | Tool | Task | TECH
2025-08-01 | RFT152D/F | Checked all AOVs(except Dist Tank 1) pressure tested and filled Feed loop | DS
2025-08-04 | RFT152F | Completed Feed checklist except things that require blend | DS
2025-08-05 | RFT152D | Completed as much of checklist as possible before new Dist Tank 1 arrives | DS
2025-08-05 | RR141D | Inspected tool to see what parts would be needed for conversion | DS
2025-08-06 | RFT152D | Re-bent tank lines and installed | DS
2025-08-07 | RFT152D | Installed electrical interconnects | DS
2025-08-11 | Other | Update training | RD
2025-08-11 | Other | Transfer RMA Items to new PCDManager.com | TW/CJ
2025-08-12 | Other | Update training, expense report and respirator fit test | RD
2025-08-12 | Other | Changed iexplorer to iexplorer_disabled.exe on the TwinCat toll in the Fab | TW
2025-08-12 | EK151 | locate NSCR parts for install in Fab52 to move to 42 | CJ
2025-08-12 | other | Help Mike Lopez with quartz cleaner in 52 fab | CJ
2025-08-13 | KT141F | Leak test the Feed tank | TW
2025-08-13 | RFT152D | Tank 1 delivery to Fab 52. | CJ
2025-08-13 | Other | Passdown | RD/TW/CJ
2025-08-14 | KT141F | Found leak on the Feed tank at the bottom of tank. Drained removed and retape. Leak is fixed. | TW
2025-08-14 | RFT152D | Remove parts from old tank and remove and repalce tank. | CJ/RD
2025-08-15 | RFT152D | Continue to connect lines and fix lines to tank. | CJ/RD
2025-08-18 | RFT152D | Pressure tested loop 2. Filled loops and filters | DS
2025-08-19 | RFT152D/F | Continued checklist, completed feed | DS
2025-08-19 | KT141F | Check electrical and plumbing to feed station and start SOO'S | RD/TW
2025-08-20 | RFT152D/F | Completed checklist, wrote FSR. Signed paperwork. Wrote RMA on FL01 drain fitting | DS
2025-08-20 | VC141D | Installed chem 1 iso valve per intel request | DS
2025-08-20 | KT141F | Finished the SOO's on the Feed station. Need couple more funtion test due to no Ethernet working. Waiting on Intel. | RD/TW
2025-08-21 | RFT152D/F | Signed and uploaded paperwork | DS
2025-08-21 | KT141D | Standby need Intel to walk loop 1 and loop 2 for pressure test. Intel LO/TO power on Dist. | RD/TW
2025-08-21 | EK1541D | Install the FT001, FT002, FT003, FT004, FT014 | RD
2025-08-22 | VB151D/F | Completed Furon valve audit | DS
2025-08-22 | EK141F | Landed Tank electrical connections. Completed upper Tank interconnects, still need to do the lower one | DS
2025-08-22 | KT141D | Pressure test the loop 1 and 2. Spray down the tanks and fill. Start SOO'S on Dist. and Blend. | RD/TW
2025-08-25 | KT141D | Continue to work on the SOO'S for blend and Dist. | RD/TW
2025-08-25 | Other | Break down wooded crates in Fab 42 PCD room due to fire hazard. | RD/CJ
2025-08-25 | XJ141D | Terminate wires in Blend and Dist. | EC
2025-08-26 | KG121D | Re-wired connector in PV202 due to loose pin | DS
2025-08-26 | KT141D | Finish SOO'S and setting up SMC. Need to figure out flow of LPC. UPW not flowing. | RD/TW
2025-08-26 | XJ141D | Install the FT001, FT002, FT003, FT004, FT014 | EC
2025-08-27 | EK141F | Installed FT002. Cut, re-bent, and flared bottom tank line. Hand over hand complete | DS
2025-08-27 | Other | Get parts from fab 52 cage and take to 42 Cage for parts needed. Get M25 for | RD/CJ
2025-08-27 | XJ141D | Connect the chaseway plumbing in the Dist. and Blend. Install the FT001 and FT002 in Feed station | EC
2025-08-28 | Other | Install lock on D08 in Fab 52. Clean Cabinet. | RD/EC
2025-08-29 | EK141F | Fixed leaks on PV004 and PV008. Continued checklist. OFA is off at the lateral. Cory to turn on OFA tuesday | DS
2025-08-29 | KT141F | Adjsut the PS001 0n Feed station, rebend lines for the atomizer slope from tank to Feed. Last test of the SOO's on feed. | RD
2025-08-29 | XJ141F | Connect the plumbing from the tank to the Feed Station. Cut and flare 1" PFA lines from the Process and Atomizer. Connect power to junction box on tank. | EC

## September
Date | Tool | Task | TECH
2025-09-02 | XJ141F | Tighten all fittings on feed station. Hand over hand | EC
2025-09-02 | Other | Collect all the Folders from Fab 52 to look over and update. | RD
2025-09-03 | SSC151D | Dan Lasley brought to our attention that the PV102 and PV202 was dropping pressure when one was disconnected. Investigated the issue and found the connection of PV202, solder overheated. Rewire and solder with new connector. | RD,EC,TW
2025-09-03 | SSC151D | Changed out PV102 the pressure was not dropping to zero. Intel provided all parts. | RD,EC,TW
2025-09-03 | EK141D | Remove single dilution and install the blend LPC. | EC
2025-09-03 | KT141D | Finish the FSR. | TW
2025-09-03 | Other | Update the Tool Folders from FAB 52. | RD
2025-09-04 | EK141D | Looking for parts in Fab 52 for LPC install. Install parts and place labeling on LPC lines. | TW,EC
2025-09-05 | EK141D | Continue to install parts on LPC. Finish install on LPC. | EC
2025-09-05 | Other | Walk tools in Fab 52 and update paperwork. | RD
2025-09-08 | EK141D | Install the Anton Parr, wiring and plumbing. Install UPW plumbing from CV055 to HV055. | EC/RD
2025-09-09 | EK141D | Remove 1/4" line from CV065 to NV01 and install the 1/8" line. Send email to Bernard and Andrew per AB HMI. Intel is in the the works of ordering 24V connection for power. | RD/TW
2025-09-09 | Other | update FSR on Chemrinse tools. | RD
2025-09-10 | Other | Update FSR's | RD/TW
2025-09-11 | KOR144D | Work on plumbing connection in Tank compartment. Connect electrical on Jbox in Tank compartment | EC
2025-09-11 | Other | Sent email on RAK151D and WK151D FSR not completed. Update other FSR's | RD, TW
2025-09-12 | KOR144D | Connected all the Plumbing. Install the Particle counter. Splice and connect the power for HMI. Connect he power from the Particle counter to the Jbox. | EC/TW
2025-09-12 | RAK151D | Gather information for FSR and finish FSR. | RD
2025-09-12 | Other | Show Andrew Dodd the delay on new Allen Bradley HMI. | RD
2025-09-15 | KOR144D | Calibrate the DT1 and DT2 M960 pump and install gaskets on bore cap and inlet/outlet connection. Tighten all fittings. | EC/TW
2025-09-16 | KOR144D | Pressure test the Supply line. Pressure test passed. Continue to fill the tank/DT1/DT2 with UPW and continue to test. | EC/TW
2025-09-17 | Other | Dan Lasley notified us to meet him at FAB 52 on every Tuesdays and Thurdays before 9am they will start testing the PV202 and PV102 on Chem Blend connection. He wants us available just incase the connection needs to be replaced and soldered | RD/TW/EC
2025-09-17 | KOR144D | Continue to test SOO | TW/EC
2025-09-18 | VB151D | Meet Dan L. at FAB 52 to check a Furon valve on VB151D. Dan showed us a video how to adjust the valve. We adjusted valve and tug test the valve handle. Handle is not staying on. Dan will update Bernard Klees. | TW/EC/RD
2025-09-18 | KOR144D | We noticed parts needed to reflect the KOR tool in Fab 52. We need to remove parts from the filter compartment and from the tank compartment. | TW/EC
2025-09-19 | RAK151D | FSR signed off. I mentioned to Dan about the IY not having an RMA created for repalcement he said not to create one. | RD
2025-09-19 | KOR144D | Finished removing parts from the filter compartment and Tank compartment. Retest to make sure no parts are leaking and function test. | TW/EC
2025-09-22 | KOR144D | Ran additional testing for leaks since we removed the filter compartment. Found and fixed a few. Ran bug tests to try re-creating the software bugs I ran into during testing. Filled out FSR/Cert of Approval. | TW/EC
2025-09-23 | KOR144D | Tried to get the tool to Dose 1, as it's the last item on our checklist. Talked with Duane to try walking me through the CR288 settings but could not get it to Dose. | TW/EC
2025-09-24 | KOR144D | Fixed leak in commons and M65. Troubleshot LPC Communication error, and Tool not Dosing. Took in passdown from Casey for NCSR/RMA next steps. | TW/EC
2025-09-25 | Other | Meet with Dan to test PV102 and PV202 on chem blends in Fab 52. No testing today. | RD/TW/EC
2025-09-29 | EK141D | Start up paperwork started, checking valves, components, Tank sensor set. On Feed Station found PV004 and PV008 leaking from weep hole. Verified with Dan that we need to replace and create an RMA for parts. | RD/EC
2025-09-26 | EK141D | Pressure switch on Blend and Dist Set 50 psi and 65 psi. tighten all fittings on Blend and Dist. Open and close CV's. | RD/EC
2025-09-26 | EK141F | Work with intel to close Main process UPW valve for the EK141F to remove and replace PV004 and PV008. Removed parts from XJ141D. Create RMA for parts. | RD/EC
2025-09-26 | EK141D | Tighten fittings on Distribution and Blend. Request with Intel to walk loop 1 and loop 2 for pressure test. | RD/EC
2025-09-29 | EK141D | Pressure Test Loop 1&2. Sorted all but 10 folders into color coded folders for organizational purposes. Updated RMA Matrix with Filters. Submited RMA on XJ PV004. Had unsigned paperwork signed by Dan. Discovered tank spray spraying too high, leaking out lid. | TW
2025-09-30 | EK141F | Fixed spray on feed tank, pressure wasn't high enough. Started looking into M65 issue. | RD.EC
2025-09-30 | Other | Down time canceld for the Porportion air. | RD,TW,EC
2025-09-30 | EK141F | After pressure test passed on the loop from Feed to Blend fill loop with UPW. Once the loop was filling the feed tank we noticed a leak on tank fitting. Report to customer, Supervisor and create an RMA. Standby for further notice. | RD,EC

## October
Date | Tool | Task | TECH
2025-10-01 | EK141F | Dan had us continue to test the feed station regardless if tank is cracked. Finished the SOO's on feed. | RD,EC
2025-10-02 | EK141D | Introduce UPW through loop 1 and loop 2. Start SOO's on Dist. and blend station. | EC/TW
2025-10-02 | BT151D/BT152D | Down time was a go on checking the Porportion Air. BT151D had no issues, BT152D had no issues with portortion air, Intel pointed out a leak on PV005. Intel provided part and we repalced. | RD,EC,TW
2025-10-03 | EK141D | Continue SOO's on Distribution. | RD,EC
2025-10-06 | EK141D | Tested alarms and SSO Blend and Distribution | EC/TW

## November
Date | Tool | Task | TECH

## December
Date | Tool | Task | TECH
2025-12-12 |  | Test1